## Test
Project | start_date | end_date | phase1_duration | phase2_duration | phase3_duration | phase4_duration | phase5_duration | phase6_duration
AFD-048-B ¦ Southwest End-Around Taxiway Construction (TWY E Extension) | 2024-03-01 | 2024-05-29 |  |  |  | 90
AFD-048-B ¦ Southwest End-Around Taxiway Construction (TWY E Extension) | 2024-05-30 | 2026-01-19 |  |  |  |  | 600
AFD-048-B ¦ Southwest End-Around Taxiway Construction (TWY E Extension) | 2026-01-20 | 2026-05-19 | [5 empty] | 120
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2032-07-01 | 2032-10-08 | 100
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2033-10-01 | 2034-01-08 | 100
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2030-10-01 | 2031-01-08 | 100
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2035-02-05 | 2035-05-15 | 100
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2030-07-05 | 2030-10-12 | 100
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2023-06-06 | 2023-09-13 | 100
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2023-09-14 | 2023-11-12 |  | 60
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2023-11-13 | 2024-08-08 |  |  | 270
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2024-08-09 | 2024-11-06 |  |  |  | 90
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2024-11-07 | 2025-11-06 |  |  |  |  | 365
OTH-006 ¦ Fire Protection Systems Repair (various bldgs.) | 2025-11-07 | 2026-03-06 | [5 empty] | 120
OTH-020 ¦ Corporate Communications Digital Signage | 2023-10-01 | 2024-01-08 | 100
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2031-07-25 | 2031-11-01 | 100
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2023-10-01 | 2035-09-30 | 4383
OTH-087 ¦ ETAM Campus Relocate | 2023-10-01 | 2024-01-28 | 120
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2024-06-30 | 2024-10-07 | 100
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2030-07-25 | 2030-11-01 | 100
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2029-09-03 | 2029-12-11 | 100
PAR-068 ¦ PCS Infrastructure Replacement | 2029-12-14 | 2030-03-23 | 100
PAR-068 ¦ PCS Infrastructure Replacement | 2030-03-24 | 2030-05-22 |  | 60
PAR-068 ¦ PCS Infrastructure Replacement | 2030-05-23 | 2030-08-20 |  |  | 90
PAR-068 ¦ PCS Infrastructure Replacement | 2030-08-21 | 2030-11-18 |  |  |  | 90
PAR-068 ¦ PCS Infrastructure Replacement | 2030-11-19 | 2031-05-17 |  |  |  |  | 180
PAR-068 ¦ PCS Infrastructure Replacement | 2031-05-18 | 2031-09-14 | [5 empty] | 120
PAR-074 ¦ Reconstruction of Lot 6E | 2023-10-01 | 2024-01-28 | 120
PAR-075 ¦ Reconstruction of Express South | 2030-10-01 | 2031-01-28 | 120
PSR-057 ¦ West 21st Street Repairs | 2023-06-06 | 2023-06-06 | 0
PSR-057 ¦ West 21st Street Repairs | 2023-06-06 | 2023-06-06 |  | 0
PSR-057 ¦ West 21st Street Repairs | 2023-06-06 | 2023-06-06 |  |  | 0
PSR-057 ¦ West 21st Street Repairs | 2023-06-06 | 2023-06-06 |  |  |  | 0
PSR-057 ¦ West 21st Street Repairs | 2023-12-01 | 2023-12-01 | [5 empty] | 0
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-06-06 | 0
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-06-06 |  | 0
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-06-06 |  |  | 0
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-06-06 |  |  |  | 0
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-07-05 | [5 empty] | 30
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2033-06-24 | 2033-10-01 | 100
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2023-10-01 | 2024-01-08 | 100
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2026-07-01 | 2027-02-25 | 240
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2028-06-30 | 2028-10-07 | 100
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2033-07-24 | 2033-10-31 | 100
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2034-07-25 | 2034-11-01 | 100
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2030-07-25 | 2030-11-01 | 100
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2030-06-29 | 2030-10-06 | 100
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2032-06-23 | 2032-09-30 | 100
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2031-06-26 | 2031-10-03 | 100
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2031-06-26 | 2031-10-03 | 100
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2023-07-01 | 2023-10-08 | 100
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2023-10-01 | 2024-01-28 | 120
RDS-190 ¦ NB Control Plaza Entrance | 2023-10-01 | 2024-01-28 | 120
RDS-191 ¦ SB Control Plaza Exit | 2023-10-01 | 2024-01-28 | 120
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2023-10-01 | 2024-01-28 | 120
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2023-10-01 | 2024-01-28 | 120
RDS-195 ¦ NB Control Plaza Exit | 2023-10-01 | 2024-01-28 | 120
RDS-196 ¦ SB Control Plaza Entrance | 2023-10-01 | 2024-01-28 | 120
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2023-10-01 | 2024-01-28 | 120
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2023-10-01 | 2024-01-28 | 120
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2023-10-01 | 2024-01-28 | 120
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2024-10-01 | 2025-01-28 | 120
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2024-10-01 | 2025-01-28 | 120
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2024-10-01 | 2025-01-28 | 120
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2025-10-01 | 2026-01-28 | 120
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2025-10-01 | 2026-01-28 | 120
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2025-10-01 | 2026-01-28 | 120
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2025-10-01 | 2026-01-28 | 120
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2025-10-01 | 2026-01-28 | 120
RDS-209 ¦ Sta 551+50 interior recirculating road | 2025-10-01 | 2026-01-28 | 120
RDS-210 ¦ Sta 542+00 road to N Express | 2025-10-01 | 2026-01-28 | 120
RDS-211 ¦ Sta 507+00 ice road | 2025-10-01 | 2026-01-28 | 120
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2025-10-01 | 2026-01-28 | 120
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2025-10-01 | 2026-01-28 | 120
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2025-10-01 | 2026-01-28 | 120
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2025-10-01 | 2026-01-28 | 120
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2026-10-01 | 2027-01-28 | 120
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2026-09-03 | 2026-12-11 | 100
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2026-12-12 | 2027-02-09 |  | 60
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2027-02-10 | 2027-08-08 |  |  | 180
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2027-08-09 | 2027-11-06 |  |  |  | 90
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2027-11-07 | 2028-10-31 |  |  |  |  | 360
SAF-074 ¦ Fire station #4 HVAC System Replacement | 2028-11-01 | 2028-12-30 | [5 empty] | 60
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2026-09-04 | 2026-12-12 | 100
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2026-10-01 | 2027-01-08 | 100
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2027-01-09 | 2027-03-09 |  | 60
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2027-03-10 | 2027-09-05 |  |  | 180
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2027-09-06 | 2027-12-04 |  |  |  | 90
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2027-12-05 | 2028-11-28 |  |  |  |  | 360
SAF-080 ¦ Backup Center for MCR and 911 Dispatch | 2028-11-29 | 2029-01-27 | [5 empty] | 60
SAF-082 ¦ Rehab Fire Station 6 | 2029-10-01 | 2030-01-08 | 100
SAF-082 ¦ Rehab Fire Station 6 | 2030-01-09 | 2030-03-09 |  | 60
SAF-082 ¦ Rehab Fire Station 6 | 2030-03-10 | 2030-09-05 |  |  | 180
SAF-082 ¦ Rehab Fire Station 6 | 2030-09-06 | 2030-12-04 |  |  |  | 90
SAF-082 ¦ Rehab Fire Station 6 | 2030-12-05 | 2031-11-29 |  |  |  |  | 360
SAF-082 ¦ Rehab Fire Station 6 | 2031-11-30 | 2032-01-28 | [5 empty] | 60
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2027-01-31 | 2027-05-10 | 100
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2027-05-11 | 2027-07-09 |  | 60
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2027-07-10 | 2028-01-05 |  |  | 180
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2028-01-06 | 2028-04-04 |  |  |  | 90
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2028-04-05 | 2029-03-30 |  |  |  |  | 360
SAF-083 ¦ Fire Station #1 Roof Replacement/Repair | 2029-03-31 | 2029-05-29 | [5 empty] | 60
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2024-12-01 | 2025-07-28 | 240
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2027-02-05 | 2027-05-15 | 100
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2026-10-01 | 2027-05-28 | 240
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2023-06-06 | 2023-09-13 | 100
TER-114 ¦ Corporate Aviation - Roof Replacement | 2027-02-05 | 2027-05-15 | 100
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2030-01-01 | 2030-04-10 | 100
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2031-04-05 | 2031-11-30 | 240
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2031-12-01 | 2031-12-01 |  | 1
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2031-12-02 | 2031-12-02 |  |  | 1
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2031-12-03 | 2031-12-03 |  |  |  | 1
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2033-12-03 | 2034-01-31 | [5 empty] | 60
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2030-02-05 | 2030-05-15 | 100
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2030-03-03 | 2030-06-10 | 100
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2030-01-01 | 2030-04-10 | 100
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2030-04-11 | 2030-06-09 |  | 60
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2030-06-10 | 2031-03-06 |  |  | 270
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2031-03-07 | 2031-06-04 |  |  |  | 90
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2031-06-05 | 2032-05-29 |  |  |  |  | 360
TER-229 ¦ Terminal D: Integrated Video Terminal Announcement System | 2032-05-30 | 2032-07-28 | [5 empty] | 60
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2029-07-06 | 2029-10-13 | 100
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2029-10-14 | 2029-12-12 |  | 60
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2029-12-13 | 2030-09-08 |  |  | 270
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2030-09-09 | 2030-12-07 |  |  |  | 90
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2030-12-08 | 2031-12-02 |  |  |  |  | 360
TER-231 ¦ Terminal D: Rooftop Canopies on Parking Garages | 2031-12-03 | 2032-01-31 | [5 empty] | 60
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2030-02-05 | 2030-05-15 | 100
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2030-05-16 | 2030-07-14 |  | 60
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2030-07-15 | 2031-04-10 |  |  | 270
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2031-04-11 | 2031-07-09 |  |  |  | 90
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2031-07-10 | 2032-07-03 |  |  |  |  | 360
TER-232 ¦ Terminal D: BHS CCTV for N/S TSA Matrices (50) | 2032-07-04 | 2032-09-01 | [5 empty] | 60
TER-239 ¦ Concessions Awareness Program | 2030-04-01 | 2030-07-09 | 100
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2027-02-05 | 2027-05-15 | 100
TER-255 ¦ Terminal B Mainline Expansion | 2024-01-03 | 2024-03-02 | [5 empty] | 60
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2023-06-06 | 2024-01-31 | 240
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2023-06-06 | 2024-01-31 | 240
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2024-05-01 | 2024-12-26 | 240
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2025-05-01 | 2025-12-26 | 240
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2026-05-01 | 2026-12-26 | 240
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2027-05-01 | 2027-12-26 | 240
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2028-05-01 | 2028-12-26 | 240
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2029-07-05 | 2030-03-01 | 240
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2023-06-06 | 2023-09-03 | 90
TER-285 ¦ Terminal Buildings Freight Elevators | 2023-06-06 | 2023-09-03 | 90
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2023-06-06 | 2023-09-03 | 90
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2035-10-01 | 2035-10-01 |  | 1
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2035-10-02 | 2035-10-02 |  |  | 1
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2035-10-03 | 2035-10-03 |  |  |  | 1
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2035-10-04 | 2035-10-04 |  |  |  |  | 1
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2035-10-05 | 2035-10-05 | [5 empty] | 1
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2023-06-06 | 2023-10-12 | 129
UTL-032 ¦ CTA TERMINALS A & B Areas | 2031-11-26 | 2032-03-04 | 100
UTL-032 ¦ CTA TERMINALS A & B Areas | 2032-03-05 | 2032-05-03 |  | 60
UTL-032 ¦ CTA TERMINALS A & B Areas | 2032-05-04 | 2033-01-28 |  |  | 270
UTL-032 ¦ CTA TERMINALS A & B Areas | 2033-01-29 | 2033-04-28 |  |  |  | 90
UTL-032 ¦ CTA TERMINALS A & B Areas | 2033-04-29 | 2034-10-25 |  |  |  |  | 545
UTL-032 ¦ CTA TERMINALS A & B Areas | 2034-10-26 | 2034-12-24 | [5 empty] | 60
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2024-01-07 | 2024-04-15 | 100
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2024-04-16 | 2024-06-14 |  | 60
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2024-06-15 | 2024-12-11 |  |  | 180
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2024-12-12 | 2025-03-11 |  |  |  | 90
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2025-03-12 | 2026-03-06 |  |  |  |  | 360
UTL-039 ¦ CHW Pumps at Terminal D Installation | 2026-03-07 | 2026-05-05 | [5 empty] | 60
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2030-06-24 | 2030-10-01 | 100
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2030-10-02 | 2030-11-30 |  | 60
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2030-12-01 | 2031-05-29 |  |  | 180
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2031-05-30 | 2031-08-27 |  |  |  | 90
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2031-08-28 | 2032-08-21 |  |  |  |  | 360
UTL-042 ¦ Rehab Energy Plaza Boiler Feedwater System | 2032-08-22 | 2032-10-20 | [5 empty] | 60
UTL-043 ¦ Boiler 10 Replacement | 2023-06-06 | 2023-09-13 | 100
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2026-09-04 | 2026-12-12 | 100
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2026-12-13 | 2027-02-10 |  | 60
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2027-02-11 | 2027-08-09 |  |  | 180
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2027-08-10 | 2027-11-07 |  |  |  | 90
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2027-11-08 | 2028-11-01 |  |  |  |  | 360
UTL-044 ¦ Energy Plaza Air Compressors and Air Dryers Replacement | 2028-11-02 | 2028-12-31 | [5 empty] | 60
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2032-07-01 | 2032-10-08 | 100
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2033-07-02 | 2033-10-09 | 100
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2030-01-03 | 2030-04-12 | 100
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2026-07-01 | 2026-10-08 | 100
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2031-11-27 | 2032-03-05 | 100
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2034-09-28 | 2035-01-05 | 100
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2026-11-28 | 2027-03-07 | 100
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2023-07-02 | 2023-10-09 | 100
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2025-09-03 | 2025-12-11 | 100
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2023-06-06 | 2023-10-09 | 126
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2026-10-01 | 2027-01-08 | 100
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2027-01-09 | 2027-03-09 |  | 60
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2027-03-10 | 2027-09-05 |  |  | 180
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2027-09-06 | 2027-12-04 |  |  |  | 90
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2027-12-05 | 2028-11-28 |  |  |  |  | 360
UTL-080 ¦ Thermal - JP 8 Pumps, Piping, and Controls Replacement | 2028-11-29 | 2029-01-27 | [5 empty] | 60
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2023-06-06 | 2024-01-31 | 240
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2024-02-01 | 2024-03-31 |  | 60
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2024-04-01 | 2024-12-26 |  |  | 270
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2024-12-27 | 2025-03-26 |  |  |  | 90
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2025-03-27 | 2026-09-17 |  |  |  |  | 540
UTL-082 ¦ Thermal - Replace Tunnel Heat Exchangers and Steam Control Valves | 2026-09-18 | 2026-11-16 | [5 empty] | 60
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2025-09-07 | 2025-12-15 | 100
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2025-12-16 | 2026-02-13 |  | 60
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2026-02-14 | 2026-05-14 |  |  | 90
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2026-05-15 | 2026-08-12 |  |  |  | 90
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2026-08-13 | 2027-02-08 |  |  |  |  | 180
UTL-086 ¦ Thermal - OM/YK and Refrigerant Monitoring Controls Rehabilitation | 2027-02-09 | 2027-04-09 | [5 empty] | 60
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2023-06-06 | 2023-09-13 | 100
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2026-09-05 | 2026-12-13 | 100
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2029-10-01 | 2030-01-28 | 120
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2029-09-28 | 2030-01-05 | 100
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2024-08-31 | 2024-12-08 | 100
UTL-153 ¦ Skylink Interior Lighting Controls | 2024-04-03 | 2024-07-11 | 100
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2023-06-06 | 2023-09-13 | 100
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2026-10-01 | 2027-01-08 | 100
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2026-06-29 | 2026-10-06 | 100
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2029-06-30 | 2029-10-07 | 100
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2029-06-27 | 2029-10-04 | 100
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2029-07-31 | 2029-11-07 | 100
UTL-166 ¦ CUP Assessment and Risk Analysis | 2029-06-28 | 2029-10-05 | 100
UTL-166 ¦ CUP Assessment and Risk Analysis | 2030-06-03 | 2030-08-31 |  |  |  | 90
UTL-166 ¦ CUP Assessment and Risk Analysis | 2030-09-01 | 2030-09-01 |  |  |  |  | 0
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2027-06-30 | 2027-10-07 | 100
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2027-10-08 | 2027-12-06 |  | 60
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2027-12-07 | 2028-03-05 |  |  | 90
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2028-03-06 | 2028-06-03 |  |  |  | 90
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2028-06-04 | 2028-11-30 |  |  |  |  | 180
UTL-178 ¦ Install Weigh Station at Reverse Osmosis Facility | 2028-12-01 | 2029-01-29 | [5 empty] | 60
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2029-07-01 | 2029-10-08 | 100
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2023-06-06 | 2023-09-13 | 100
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2029-09-02 | 2029-12-10 | 100
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2026-09-04 | 2026-12-12 | 100
UTL-205 ¦ Skylink Obsolescence | 2023-10-01 | 2023-10-01 | 0
UTL-205 ¦ Skylink Obsolescence | 2023-10-01 | 2023-10-01 |  | 0
UTL-205 ¦ Skylink Obsolescence | 2023-10-01 | 2023-10-01 |  |  | 0
UTL-205 ¦ Skylink Obsolescence | 2023-10-01 | 2023-10-01 |  |  |  | 0
UTL-205 ¦ Skylink Obsolescence | 2031-10-01 | 2031-10-01 | [5 empty] | 0
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-06-06 | 0
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-06-06 |  | 0
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-06-06 |  |  |  | 0
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-07-05 | [5 empty] | 30
PSR-064 ¦ Repair Hot Water Pipe to Hyatt Regency Facility | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
UTL-205 ¦ Skylink Obsolescence | 2023-10-01 | 2031-09-30 |  |  |  |  | 2922
UTL-221 ¦ Urgent Stormwater Infra Rehab Airside FY23 | 2023-06-06 | 2023-06-06 |  |  | 0
AFD-057 ¦ Taxiway A Improvements | 2024-08-31 | 2025-04-27 | 240
AFD-057 ¦ Taxiway A Improvements | 2025-04-28 | 2025-07-26 |  | 90
AFD-057 ¦ Taxiway A Improvements | 2025-07-27 | 2026-04-22 |  |  | 270
AFD-057 ¦ Taxiway A Improvements | 2026-04-23 | 2026-07-21 |  |  |  | 90
AFD-057 ¦ Taxiway A Improvements | 2026-07-22 | 2027-12-03 |  |  |  |  | 500
AFD-057 ¦ Taxiway A Improvements | 2027-12-04 | 2028-04-01 | [5 empty] | 120
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2032-10-09 | 2033-01-06 |  | 90
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2033-01-07 | 2033-10-03 |  |  | 270
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2033-10-04 | 2034-01-01 |  |  |  | 90
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2034-01-02 | 2034-06-30 |  |  |  |  | 180
AFD-063 ¦ Taxiway B Rehabilitation (Including Bridge) | 2034-07-01 | 2034-10-28 | [5 empty] | 120
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2034-01-09 | 2034-03-09 |  | 60
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2034-03-10 | 2035-03-04 |  |  | 360
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2035-03-05 | 2035-06-02 |  |  |  | 90
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2035-06-03 | 2036-10-14 |  |  |  |  | 500
AFD-067 ¦ Runway 17L/35R Rehabilitation | 2036-10-15 | 2037-02-11 | [5 empty] | 120
AFD-071-A ¦ Runway 18L/36R Rehabilitation | 2026-10-01 | 2027-05-28 | 240
AFD-071-A ¦ Runway 18L/36R Rehabilitation | 2027-05-29 | 2027-09-05 |  | 100
AFD-071-A ¦ Runway 18L/36R Rehabilitation | 2027-09-06 | 2029-01-17 |  |  | 500
AFD-071-B ¦ Runway 18L/36R Rehabilitation | 2029-01-18 | 2029-04-17 |  |  |  | 90
AFD-071-B ¦ Runway 18L/36R Rehabilitation | 2029-04-18 | 2030-08-30 |  |  |  |  | 500
AFD-071-B ¦ Runway 18L/36R Rehabilitation | 2030-08-31 | 2030-12-28 | [5 empty] | 120
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2026-10-01 | 2027-05-28 | 240
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2027-05-29 | 2027-07-27 |  | 60
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2027-07-28 | 2027-10-25 |  |  | 90
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2027-10-26 | 2028-01-23 |  |  |  | 90
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2028-01-24 | 2028-04-22 |  |  |  |  | 90
AFD-113 ¦ Runway 17C/35C Mill and Overlay | 2028-04-23 | 2028-08-20 | [5 empty] | 120
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2028-06-27 | 2029-02-21 | 240
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2029-02-22 | 2029-04-22 |  | 60
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2029-04-23 | 2029-07-21 |  |  | 90
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2029-07-22 | 2029-10-19 |  |  |  | 90
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2029-10-20 | 2030-01-17 |  |  |  |  | 90
AFD-118 ¦ Runway 18R/36L Mill and Overlay | 2030-01-18 | 2030-05-17 | [5 empty] | 120
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2031-01-09 | 2031-03-09 |  | 60
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2031-03-10 | 2031-06-07 |  |  | 90
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2031-06-08 | 2031-09-05 |  |  |  | 90
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2031-09-06 | 2031-12-04 |  |  |  |  | 90
AFD-119 ¦ Runway 17R/35L Mill and Overlay | 2031-12-05 | 2032-04-02 | [5 empty] | 120
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2035-05-16 | 2035-07-14 |  | 60
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2035-07-15 | 2035-10-12 |  |  | 90
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2035-10-13 | 2036-01-10 |  |  |  | 90
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2036-01-11 | 2036-04-09 |  |  |  |  | 90
AFD-125 ¦ Runway 18L/36R Mill and Overlay | 2036-04-10 | 2036-08-07 | [5 empty] | 120
AFD-140-A ¦ West Airfield Lighting Vault (Design) | 2024-02-01 | 2024-09-27 | 240
AFD-140-A ¦ West Airfield Lighting Vault (Design) | 2024-09-28 | 2024-11-15 |  | 49
AFD-140-A ¦ West Airfield Lighting Vault (Design) | 2024-11-16 | 2025-07-30 |  |  | 257
AFD-140-B ¦ West Airfield Lighting Vault - Phase 1 (Construction) | 2026-10-15 | 2027-02-13 |  |  |  | 122
AFD-140-B ¦ West Airfield Lighting Vault - Phase 1 (Construction) | 2027-02-14 | 2028-02-08 |  |  |  |  | 360
AFD-140-B ¦ West Airfield Lighting Vault - Phase 1 (Construction) | 2028-02-09 | 2028-06-07 | [5 empty] | 120
AFD-140-C ¦ West Airfield Lighting Vault - Phase 2 (Construction) | 2028-10-15 | 2029-02-13 |  |  |  | 122
AFD-140-C ¦ West Airfield Lighting Vault - Phase 2 (Construction) | 2029-02-14 | 2030-02-08 |  |  |  |  | 360
AFD-140-C ¦ West Airfield Lighting Vault - Phase 2 (Construction) | 2030-02-09 | 2030-06-08 | [5 empty] | 120
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2034-06-01 | 2035-01-26 | 240
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2035-01-27 | 2035-03-16 |  | 49
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2035-03-17 | 2035-11-28 |  |  | 257
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2035-11-29 | 2036-03-29 |  |  |  | 122
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2036-03-30 | 2036-07-27 |  |  |  |  | 120
AFD-143 ¦ Runways (13L/31R Minor Rehab) | 2036-07-28 | 2036-11-24 | [5 empty] | 120
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2023-06-06 | 2024-01-31 | 240
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2024-02-01 | 2024-03-20 |  | 49
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2024-03-21 | 2024-12-02 |  |  | 257
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2024-12-03 | 2025-04-03 |  |  |  | 122
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2025-04-04 | 2025-08-01 |  |  |  |  | 120
AFD-144 ¦ CTA Ramp Rehab - Terminal A (Design and Construction) | 2025-08-02 | 2025-11-29 | [5 empty] | 120
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2027-10-01 | 2028-05-27 | 240
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2028-05-28 | 2028-07-15 |  | 49
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2028-07-16 | 2029-03-29 |  |  | 257
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2029-03-30 | 2029-07-29 |  |  |  | 122
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2029-07-30 | 2029-11-26 |  |  |  |  | 120
AFD-145 ¦ Taxiway A Bridge (design and construction) | 2029-11-27 | 2030-03-26 | [5 empty] | 120
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2025-10-01 | 2026-05-28 | 240
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2026-05-29 | 2026-07-16 |  | 49
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2026-07-17 | 2027-03-30 |  |  | 257
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2027-03-31 | 2027-07-30 |  |  |  | 122
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2027-07-31 | 2027-11-27 |  |  |  |  | 120
AFD-NEW ¦ CTA Ramp Rehab - Terminal C (design and construction) | 2027-11-28 | 2028-03-26 | [5 empty] | 120
TER-175 ¦ Terminal C: Jetbridge Replacement (High Gates) | 2031-12-04 | 2033-12-02 |  |  |  |  | 730
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2030-01-29 | 2030-04-28 |  | 90
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2030-04-29 | 2030-11-15 |  |  | 201
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2030-11-16 | 2031-02-13 |  |  |  | 90
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2031-02-14 | 2031-12-10 |  |  |  |  | 300
UTL-139 ¦ Rehabilitate Sewer Mains at West of Taxiway EL | 2031-12-11 | 2032-04-08 | [5 empty] | 120
OTH-020 ¦ Corporate Communications Digital Signage | 2024-01-09 | 2024-03-08 |  | 60
OTH-020 ¦ Corporate Communications Digital Signage | 2024-03-09 | 2024-09-04 |  |  | 180
OTH-020 ¦ Corporate Communications Digital Signage | 2024-09-05 | 2024-12-03 |  |  |  | 90
OTH-020 ¦ Corporate Communications Digital Signage | 2024-12-04 | 2025-12-03 |  |  |  |  | 365
OTH-020 ¦ Corporate Communications Digital Signage | 2025-12-04 | 2026-04-02 | [5 empty] | 120
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2035-10-01 | 2035-10-01 |  | 1
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2035-10-02 | 2035-10-02 |  |  | 1
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2035-10-03 | 2035-10-03 |  |  |  | 1
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2035-10-04 | 2035-10-04 |  |  |  |  | 1
OTH-086-A ¦ Conveyances Rehab (PROGRAM) | 2035-10-05 | 2035-10-05 | [5 empty] | 1
OTH-087 ¦ ETAM Campus Relocate | 2024-01-29 | 2024-12-06 |  | 313
OTH-087 ¦ ETAM Campus Relocate | 2024-12-07 | 2025-02-02 |  |  | 58
OTH-087 ¦ ETAM Campus Relocate | 2025-02-03 | 2025-09-23 |  |  |  | 232
OTH-087 ¦ ETAM Campus Relocate | 2025-09-23 | 2026-01-11 |  |  |  |  | 110
OTH-087 ¦ ETAM Campus Relocate | 2026-01-11 | 2026-07-10 | [5 empty] | 180
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2029-12-12 | 2030-02-09 |  | 60
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2030-02-10 | 2030-08-08 |  |  | 180
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2030-08-09 | 2030-11-06 |  |  |  | 90
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2030-11-07 | 2031-11-01 |  |  |  |  | 360
PAR-049 ¦ Ground Transportation (GT) Break Room in Terminal B | 2031-11-02 | 2031-12-31 | [5 empty] | 60
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2029-10-01 | 2030-05-28 | 240
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2030-05-29 | 2030-08-26 |  | 90
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2030-08-27 | 2031-06-10 |  |  | 288
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2031-06-11 | 2031-10-04 |  |  |  | 116
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2031-10-05 | 2032-05-31 |  |  |  |  | 240
SAF-047 ¦ DPS Indoor Gun Range - Design and Build | 2032-06-01 | 2032-09-28 | [5 empty] | 120
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2026-12-13 | 2027-02-10 |  | 60
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2027-02-11 | 2027-08-09 |  |  | 180
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2027-08-10 | 2027-11-07 |  |  |  | 90
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2027-11-08 | 2028-11-01 |  |  |  |  | 360
SAF-075 ¦ Fire station #6 HVAC System Replacement | 2028-11-02 | 2028-12-31 | [5 empty] | 60
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2025-07-29 | 2025-09-26 |  | 60
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2025-09-27 | 2026-03-25 |  |  | 180
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2026-03-26 | 2026-06-23 |  |  |  | 90
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2026-06-24 | 2026-12-20 |  |  |  |  | 180
SAF-084 ¦ 2020 Non-Terminal Roofing and Waterproofing | 2026-12-21 | 2027-02-18 | [5 empty] | 60
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2027-05-16 | 2027-07-14 |  | 60
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2027-07-15 | 2028-01-10 |  |  | 180
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2028-01-11 | 2028-04-09 |  |  |  | 90
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2028-04-10 | 2029-04-09 |  |  |  |  | 365
TER-004 ¦ Terminal A - C Connector Roof Replacement | 2029-04-10 | 2029-08-07 | [5 empty] | 120
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2027-05-29 | 2027-07-30 |  | 63
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2027-07-31 | 2028-02-05 |  |  | 190
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2028-02-06 | 2028-06-04 |  |  |  | 120
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2028-06-05 | 2030-08-25 |  |  |  |  | 812
TER-021-B ¦ Terminal D Elevator Rehabilitation | 2030-08-26 | 2030-12-23 | [5 empty] | 120
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2023-09-14 | 2023-11-12 |  | 60
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2023-11-13 | 2024-05-12 |  |  | 182
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2024-05-13 | 2024-08-11 |  |  |  | 91
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2024-08-12 | 2025-08-11 |  |  |  |  | 365
TER-038 ¦ Terminal E Integrate TRIP BAS with existing PCA (26 gates)/Fixed Walkway (12 gates) | 2025-08-12 | 2025-10-10 | [5 empty] | 60
TER-070 ¦ Terminal B Roofing Project | 2027-10-01 | 2028-05-27 | 240
TER-070 ¦ Terminal B Roofing Project | 2028-05-28 | 2028-07-15 |  | 49
TER-070 ¦ Terminal B Roofing Project | 2028-07-16 | 2029-03-22 |  |  | 250
TER-070 ¦ Terminal B Roofing Project | 2029-03-23 | 2029-08-17 |  |  |  | 148
TER-070 ¦ Terminal B Roofing Project | 2029-08-18 | 2029-12-15 |  |  |  |  | 120
TER-070 ¦ Terminal B Roofing Project | 2029-12-16 | 2030-04-14 | [5 empty] | 120
TER-114 ¦ Corporate Aviation - Roof Replacement | 2027-05-16 | 2027-07-14 |  | 60
TER-114 ¦ Corporate Aviation - Roof Replacement | 2027-07-15 | 2028-01-10 |  |  | 180
TER-114 ¦ Corporate Aviation - Roof Replacement | 2028-01-11 | 2028-04-09 |  |  |  | 90
TER-114 ¦ Corporate Aviation - Roof Replacement | 2028-04-10 | 2029-04-09 |  |  |  |  | 365
TER-114 ¦ Corporate Aviation - Roof Replacement | 2029-04-10 | 2029-08-07 | [5 empty] | 120
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2030-04-11 | 2030-06-09 |  | 60
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2030-06-10 | 2030-09-07 |  |  | 90
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2030-09-08 | 2030-12-06 |  |  |  | 90
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2030-12-07 | 2031-06-04 |  |  |  |  | 180
TER-144 ¦ Terminal A, B, & E: Hydronic & HVAC System Performance Testing | 2031-06-05 | 2031-10-02 | [5 empty] | 120
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2030-05-16 | 2030-07-14 |  | 60
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2030-07-15 | 2030-10-12 |  |  | 90
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2030-10-13 | 2031-01-10 |  |  |  | 90
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2031-01-11 | 2031-04-10 |  |  |  |  | 90
TER-216 ¦ Term A9 & C39 Trit Conversion (closed loop sys) | 2031-04-11 | 2031-08-08 | [5 empty] | 120
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2030-06-11 | 2030-08-09 |  | 60
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2030-08-10 | 2031-02-05 |  |  | 180
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2031-02-06 | 2031-05-06 |  |  |  | 90
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2031-05-07 | 2031-11-02 |  |  |  |  | 180
TER-226 ¦ Terminal D: HVAC Equipment Replacement in Pedestrian Bridges to Garages | 2031-11-03 | 2032-01-01 | [5 empty] | 60
TER-236 ¦ Holistic Airside Restrooms Program (HARP) | 2023-10-01 | 2026-09-30 | 1096
TER-239 ¦ Concessions Awareness Program | 2030-07-10 | 2030-09-07 |  | 60
TER-239 ¦ Concessions Awareness Program | 2030-09-08 | 2031-06-04 |  |  | 270
TER-239 ¦ Concessions Awareness Program | 2031-06-05 | 2031-09-02 |  |  |  | 90
TER-239 ¦ Concessions Awareness Program | 2031-09-03 | 2032-09-01 |  |  |  |  | 365
TER-239 ¦ Concessions Awareness Program | 2032-09-02 | 2032-12-30 | [5 empty] | 120
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2027-05-16 | 2027-07-14 |  | 60
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2027-07-15 | 2027-10-12 |  |  | 90
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2027-10-13 | 2028-01-10 |  |  |  | 90
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2028-01-11 | 2028-07-08 |  |  |  |  | 180
TER-245 ¦ Terminal C: Skylink Connection Escalator Step Tread Rehabilitation | 2028-07-09 | 2028-11-05 | [5 empty] | 120
TER-258-B ¦ Program Development for Baggage Handling System Improvements | 2023-06-06 | 2024-09-30 |  |  |  |  | 483
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2024-02-01 | 2024-03-31 |  | 60
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2024-04-01 | 2025-01-25 |  |  | 300
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2025-01-26 | 2025-04-25 |  |  |  | 90
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2025-04-26 | 2026-04-20 |  |  |  |  | 360
TER-274-B ¦ Passenger Boarding Bridges Program #1-B | 2026-04-21 | 2026-06-19 | [5 empty] | 60
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2024-02-01 | 2024-03-31 |  | 60
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2024-04-01 | 2025-01-25 |  |  | 300
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2025-01-26 | 2025-04-25 |  |  |  | 90
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2025-04-26 | 2026-04-20 |  |  |  |  | 360
TER-275 ¦ Passenger Boarding Bridges Program #2 | 2026-04-21 | 2026-06-19 | [5 empty] | 60
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2024-12-27 | 2025-02-24 |  | 60
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2025-02-25 | 2025-12-21 |  |  | 300
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2025-12-22 | 2026-03-21 |  |  |  | 90
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2026-03-22 | 2027-03-16 |  |  |  |  | 360
TER-275-A ¦ Passenger Boarding Bridges Program #2-A | 2027-03-17 | 2027-05-15 | [5 empty] | 60
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2025-12-27 | 2026-02-24 |  | 60
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2026-02-25 | 2026-12-21 |  |  | 300
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2026-12-22 | 2027-03-21 |  |  |  | 90
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2027-03-22 | 2028-03-15 |  |  |  |  | 360
TER-275-B ¦ Passenger Boarding Bridges Program #2-B | 2028-03-16 | 2028-05-14 | [5 empty] | 60
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2026-12-27 | 2027-02-24 |  | 60
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2027-02-25 | 2027-12-21 |  |  | 300
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2027-12-22 | 2028-03-20 |  |  |  | 90
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2028-03-21 | 2029-03-15 |  |  |  |  | 360
TER-276 ¦ Passenger Boarding Bridges Program #3 | 2029-03-16 | 2029-05-14 | [5 empty] | 60
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2027-12-27 | 2028-02-24 |  | 60
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2028-02-25 | 2028-12-20 |  |  | 300
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2028-12-21 | 2029-03-20 |  |  |  | 90
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2029-03-21 | 2030-03-15 |  |  |  |  | 360
TER-276-A ¦ Passenger Boarding Bridges Program #3-A | 2030-03-16 | 2030-05-14 | [5 empty] | 60
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2028-12-27 | 2029-02-24 |  | 60
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2029-02-25 | 2029-12-21 |  |  | 300
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2029-12-22 | 2030-03-21 |  |  |  | 90
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2030-03-22 | 2031-03-16 |  |  |  |  | 360
TER-276-B ¦ Passenger Boarding Bridges Program #3-B | 2031-03-17 | 2031-05-15 | [5 empty] | 60
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2030-03-02 | 2030-04-30 |  | 60
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2030-05-01 | 2031-02-24 |  |  | 300
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2031-02-25 | 2031-05-25 |  |  |  | 90
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2031-05-26 | 2032-05-19 |  |  |  |  | 360
TER-277 ¦ Passenger Boarding Bridges Program #4 | 2032-05-20 | 2032-07-18 | [5 empty] | 60
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2023-09-04 | 2023-11-02 |  | 60
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2023-11-03 | 2024-04-30 |  |  | 180
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2024-05-01 | 2024-07-29 |  |  |  | 90
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2024-07-30 | 2025-04-25 |  |  |  |  | 270
TER-282 ¦ Terminal D Exhaust and Relief Fans Replacement | 2025-04-26 | 2025-08-23 | [5 empty] | 120
TER-285 ¦ Terminal Buildings Freight Elevators | 2023-09-04 | 2023-11-02 |  | 60
TER-285 ¦ Terminal Buildings Freight Elevators | 2023-11-03 | 2024-04-30 |  |  | 180
TER-285 ¦ Terminal Buildings Freight Elevators | 2024-05-01 | 2024-07-29 |  |  |  | 90
TER-285 ¦ Terminal Buildings Freight Elevators | 2024-07-30 | 2025-04-25 |  |  |  |  | 270
TER-285 ¦ Terminal Buildings Freight Elevators | 2025-04-26 | 2025-08-23 | [5 empty] | 120
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2023-09-04 | 2023-11-02 |  | 60
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2023-11-03 | 2024-04-30 |  |  | 180
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2024-05-01 | 2024-07-29 |  |  |  | 90
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2024-07-30 | 2025-04-25 |  |  |  |  | 270
TER-288 ¦ Terminal D Automatic Sliding Door Replacement | 2025-04-26 | 2025-08-23 | [5 empty] | 120
TER-291 ¦ Other Facility Rehabilitation Projects (Ongoing Assessments) | 2023-06-06 | 2035-09-30 | 4500
UTL-153 ¦ Skylink Interior Lighting Controls | 2024-07-12 | 2024-09-09 |  | 60
UTL-153 ¦ Skylink Interior Lighting Controls | 2024-09-10 | 2025-03-08 |  |  | 180
UTL-153 ¦ Skylink Interior Lighting Controls | 2025-03-09 | 2025-06-06 |  |  |  | 90
UTL-153 ¦ Skylink Interior Lighting Controls | 2025-06-07 | 2026-06-01 |  |  |  |  | 360
UTL-153 ¦ Skylink Interior Lighting Controls | 2026-06-02 | 2026-07-31 | [5 empty] | 60
UTL-166 ¦ CUP Assessment and Risk Analysis | 2029-10-06 | 2029-12-04 |  | 60
UTL-166 ¦ CUP Assessment and Risk Analysis | 2029-12-05 | 2030-06-02 |  |  | 180
UTL-166 ¦ CUP Assessment and Risk Analysis | 2030-09-01 | 2030-10-30 | [5 empty] | 60
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2023-09-14 | 2023-11-12 |  | 60
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2023-11-13 | 2024-05-10 |  |  | 180
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2024-05-11 | 2024-08-08 |  |  |  | 90
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2024-08-09 | 2025-08-03 |  |  |  |  | 360
UTL-182 ¦ Rental Car Center: Sliding Doors Controls Upgrade | 2025-08-04 | 2025-10-02 | [5 empty] | 60
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2023-09-14 | 2023-12-12 |  | 90
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2023-12-13 | 2024-08-08 |  |  | 240
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2024-08-09 | 2024-11-06 |  |  |  | 90
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2024-11-07 | 2025-11-01 |  |  |  |  | 360
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2025-11-02 | 2026-01-30 | [5 empty] | 90
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2030-10-13 | 2030-12-11 |  | 60
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2030-12-12 | 2031-06-09 |  |  | 180
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2031-06-10 | 2031-09-07 |  |  |  | 90
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2031-09-08 | 2032-09-06 |  |  |  |  | 365
ENV-001 ¦ Wastewater Dumping Station @ Pre-Treatment Plant (PTP) | 2032-09-07 | 2033-01-04 | [5 empty] | 120
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2031-11-02 | 2031-12-31 |  | 60
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2032-01-01 | 2032-06-28 |  |  | 180
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2032-06-29 | 2032-09-26 |  |  |  | 90
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2032-09-27 | 2033-09-26 |  |  |  |  | 365
OTH-026-H ¦ Replace Main Sanitary Sewer Line Phase 2 | 2033-09-27 | 2034-01-24 | [5 empty] | 120
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2024-10-08 | 2024-12-06 |  | 60
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2024-12-07 | 2025-06-04 |  |  | 180
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2025-06-05 | 2025-09-02 |  |  |  | 90
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2025-09-03 | 2026-03-01 |  |  |  |  | 180
PAR-009 ¦ Remote Parking Facility Rehabilitation | 2026-03-02 | 2026-06-29 | [5 empty] | 120
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2030-11-02 | 2030-12-31 |  | 60
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2031-01-01 | 2031-03-31 |  |  | 90
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2031-04-01 | 2031-06-29 |  |  |  | 90
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2031-06-30 | 2031-09-27 |  |  |  |  | 90
PAR-013 ¦ 5E Crossover PCS Gate Redundancy | 2031-09-28 | 2032-01-25 | [5 empty] | 120
PAR-074 ¦ Reconstruction of Lot 6E | 2024-01-29 | 2024-04-27 |  | 90
PAR-074 ¦ Reconstruction of Lot 6E | 2024-04-28 | 2024-12-23 |  |  | 240
PAR-074 ¦ Reconstruction of Lot 6E | 2024-12-24 | 2025-03-23 |  |  |  | 90
PAR-074 ¦ Reconstruction of Lot 6E | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
PAR-074 ¦ Reconstruction of Lot 6E | 2026-09-15 | 2027-01-12 | [5 empty] | 120
PAR-075 ¦ Reconstruction of Express South | 2031-01-29 | 2031-04-28 |  | 90
PAR-075 ¦ Reconstruction of Express South | 2031-04-29 | 2031-12-24 |  |  | 240
PAR-075 ¦ Reconstruction of Express South | 2031-12-25 | 2032-03-23 |  |  |  | 90
PAR-075 ¦ Reconstruction of Express South | 2032-03-24 | 2033-09-14 |  |  |  |  | 540
PAR-075 ¦ Reconstruction of Express South | 2033-09-15 | 2034-01-12 | [5 empty] | 120
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2033-10-02 | 2033-11-30 |  | 60
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2033-12-01 | 2034-05-29 |  |  | 180
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2034-05-30 | 2034-08-27 |  |  |  | 90
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2034-08-28 | 2035-08-27 |  |  |  |  | 365
RDS-010 ¦ Skylink Stations/Cars - Blue Light + PA/VE (Safety) | 2035-08-28 | 2035-10-26 | [5 empty] | 60
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2024-01-09 | 2024-03-08 |  | 60
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2024-03-09 | 2024-12-03 |  |  | 270
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2024-12-04 | 2025-03-03 |  |  |  | 90
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2025-03-04 | 2026-03-03 |  |  |  |  | 365
RDS-030 ¦ Landside Roads & Bridges Rehabilitation Phase 5 | 2026-03-04 | 2026-05-02 | [5 empty] | 60
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2025-06-30 | 2026-02-24 | 240
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2026-02-25 | 2026-04-25 |  | 60
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2026-04-26 | 2026-12-21 |  |  | 240
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2026-12-22 | 2027-03-21 |  |  |  | 90
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2027-03-22 | 2028-03-20 |  |  |  |  | 365
RDS-034 ¦ 2-5W & 2-5E Bridges IP & SR Refurb (Crossunder #6 to Crossunder @5E) | 2028-03-21 | 2028-05-19 | [5 empty] | 60
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2024-08-01 | 2025-03-28 | 240
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2025-03-29 | 2025-05-27 |  | 60
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2025-05-28 | 2026-02-21 |  |  | 270
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2026-02-22 | 2026-05-22 |  |  |  | 90
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2026-05-23 | 2027-05-22 |  |  |  |  | 365
RDS-036 ¦ 2-6W & 2-6E Bridges @ Crossunder #7 IP & SR Refurb (DVOT to Crossunder #6) | 2027-05-23 | 2027-07-21 | [5 empty] | 60
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2027-02-26 | 2027-04-26 |  | 60
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2027-04-27 | 2028-01-21 |  |  | 270
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2028-01-22 | 2028-04-20 |  |  |  | 90
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2028-04-21 | 2030-04-10 |  |  |  |  | 720
RDS-037 ¦ Terminal E IP & SR Bridges and Terminal E Upper/Lower Curbsides | 2030-04-11 | 2030-06-09 | [5 empty] | 60
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2027-10-01 | 2028-05-27 | 240
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2028-05-28 | 2028-07-26 |  | 60
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2028-07-27 | 2029-04-22 |  |  | 270
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2029-04-23 | 2029-07-21 |  |  |  | 90
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2029-07-22 | 2031-07-11 |  |  |  |  | 720
RDS-038 ¦ NB IP & SR Refurb (Terminal E to Crossunder #4) | 2031-07-12 | 2031-09-09 | [5 empty] | 60
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2027-07-01 | 2028-02-25 | 240
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2028-02-26 | 2028-04-25 |  | 60
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2028-04-26 | 2029-01-20 |  |  | 270
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2029-01-21 | 2029-04-20 |  |  |  | 90
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2029-04-21 | 2031-04-10 |  |  |  |  | 720
RDS-039 ¦ 1-5W, 1-5E, 4-5E, 5-5E, 6-5E at Cross SE. SE Carousel Refurb. | 2031-04-11 | 2031-06-09 | [5 empty] | 60
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2028-10-08 | 2028-12-06 |  | 60
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2028-12-07 | 2029-06-04 |  |  | 180
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2029-06-05 | 2029-09-02 |  |  |  | 90
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2029-09-03 | 2030-05-30 |  |  |  |  | 270
RDS-044 ¦ Terminal Upper Level Roadway Re-Coating (Terminal B, C, & E) | 2030-05-31 | 2030-07-29 | [5 empty] | 60
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2033-11-01 | 2033-12-30 |  | 60
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2033-12-31 | 2034-06-28 |  |  | 180
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2034-06-29 | 2034-09-26 |  |  |  | 90
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2034-09-27 | 2035-09-26 |  |  |  |  | 365
RDS-057 ¦ NB Int'l Pkwy Bridge (1-1E) Over Ramp C-1S, Ramp C-1N (1974) | 2035-09-27 | 2036-01-24 | [5 empty] | 120
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2034-11-02 | 2034-12-31 |  | 60
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2035-01-01 | 2035-06-29 |  |  | 180
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2035-06-30 | 2035-09-27 |  |  |  | 90
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2035-09-28 | 2036-09-26 |  |  |  |  | 365
RDS-058 ¦ NB Int'l Pkwy Bridge (2-3E) at Ramp C-3S, Ramp C-3N (1974) | 2036-09-27 | 2037-01-24 | [5 empty] | 120
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2030-11-02 | 2030-12-31 |  | 60
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2031-01-01 | 2031-06-29 |  |  | 180
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2031-06-30 | 2031-09-27 |  |  |  | 90
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2031-09-28 | 2032-09-26 |  |  |  |  | 365
RDS-059 ¦ NB Ramp Bridge (5-2W) Terminal B (1971) | 2032-09-27 | 2033-01-24 | [5 empty] | 120
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2030-10-07 | 2030-12-05 |  | 60
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2030-12-06 | 2031-06-03 |  |  | 180
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2031-06-04 | 2031-09-01 |  |  |  | 90
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2031-09-02 | 2032-05-28 |  |  |  |  | 270
RDS-060 ¦ NB Ramp Bridge (7-4E) to Terminal E (1971) | 2032-05-29 | 2032-09-25 | [5 empty] | 120
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2032-10-01 | 2032-11-29 |  | 60
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2032-11-30 | 2033-08-26 |  |  | 270
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2033-08-27 | 2033-11-24 |  |  |  | 90
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2033-11-25 | 2034-11-24 |  |  |  |  | 365
RDS-066 ¦ Ramp A-4S Bridge (1-4W) at SB Int'l Pkwy SB Service Rd. (1974) | 2034-11-25 | 2035-03-24 | [5 empty] | 120
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2031-10-04 | 2031-12-02 |  | 60
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2031-12-03 | 2032-03-01 |  |  | 90
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2032-03-02 | 2032-05-30 |  |  |  | 90
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2032-05-31 | 2033-02-24 |  |  |  |  | 270
RDS-069 ¦ SB Bridge (6-3E) to Terminal C (1971) | 2033-02-25 | 2033-06-24 | [5 empty] | 120
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2031-10-04 | 2031-12-02 |  | 60
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2031-12-03 | 2032-03-31 |  |  | 120
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2032-04-01 | 2032-06-29 |  |  |  | 90
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2032-06-30 | 2033-03-26 |  |  |  |  | 270
RDS-070 ¦ SB Service Rd. Bridge (6-2W) at Ramp C-2S, Ramp C-2N (1974) | 2033-03-27 | 2033-07-24 | [5 empty] | 120
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2023-10-09 | 2023-12-07 |  | 60
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2023-12-08 | 2024-03-06 |  |  | 90
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2024-03-07 | 2024-06-04 |  |  |  | 90
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2024-06-05 | 2024-09-02 |  |  |  |  | 90
RDS-172 ¦ Terminal C Deplaning Bridge (3E DEP) at Terminal C (1973) | 2024-09-03 | 2024-12-31 | [5 empty] | 120
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2025-10-01 | 2026-05-28 | 240
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2026-05-29 | 2026-07-23 |  | 56
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2026-07-24 | 2027-03-08 |  |  | 228
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2027-03-09 | 2027-07-20 |  |  |  | 134
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2027-07-21 | 2027-11-17 |  |  |  |  | 120
RDS-187 ¦ Reconstruction of Aircraft Bridges EL and ER Wing Walls | 2027-11-18 | 2028-03-16 | [5 empty] | 120
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2024-01-29 | 2024-04-27 |  | 90
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-189 ¦ IP NB Sta 294+00 to South Airfield Drive Bridge | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-190 ¦ NB Control Plaza Entrance | 2024-01-29 | 2024-04-27 |  | 90
RDS-190 ¦ NB Control Plaza Entrance | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-190 ¦ NB Control Plaza Entrance | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-190 ¦ NB Control Plaza Entrance | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-190 ¦ NB Control Plaza Entrance | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-191 ¦ SB Control Plaza Exit | 2024-01-29 | 2024-04-27 |  | 90
RDS-191 ¦ SB Control Plaza Exit | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-191 ¦ SB Control Plaza Exit | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-191 ¦ SB Control Plaza Exit | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-191 ¦ SB Control Plaza Exit | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2024-01-29 | 2024-04-27 |  | 90
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-192 ¦ IP SB Sta 294+00 to South Airfield Drive Bridge | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2024-01-29 | 2024-04-27 |  | 90
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-194 ¦ NB IP from BR 10 (1-5E) to BR 58 (9-2E) and bridges 1-5E ice road, 3-4E CU#5 | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-195 ¦ NB Control Plaza Exit | 2024-01-29 | 2024-04-27 |  | 90
RDS-195 ¦ NB Control Plaza Exit | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-195 ¦ NB Control Plaza Exit | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-195 ¦ NB Control Plaza Exit | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-195 ¦ NB Control Plaza Exit | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-196 ¦ SB Control Plaza Entrance | 2024-01-29 | 2024-04-27 |  | 90
RDS-196 ¦ SB Control Plaza Entrance | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-196 ¦ SB Control Plaza Entrance | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-196 ¦ SB Control Plaza Entrance | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-196 ¦ SB Control Plaza Entrance | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2024-01-29 | 2024-04-27 |  | 90
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-197 ¦ SB from BR 57 (9-2W) to BR 11 (1-5W) and bridges 2-2W | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2024-01-29 | 2024-04-27 |  | 90
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-198 ¦ IP and Service Roads Partial Rehabilitation Ph 1 | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2024-01-29 | 2024-04-27 |  | 90
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2024-04-28 | 2024-12-23 |  |  | 240
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2024-12-24 | 2025-03-23 |  |  |  | 90
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2025-03-24 | 2026-09-14 |  |  |  |  | 540
RDS-199 ¦ Arterial Roads Rehab and Reconstruct Phase 2 | 2026-09-15 | 2027-01-12 | [5 empty] | 120
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2025-01-29 | 2025-04-28 |  | 90
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2025-04-29 | 2025-12-24 |  |  | 240
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2025-12-25 | 2026-03-24 |  |  |  | 90
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2026-03-25 | 2027-09-15 |  |  |  |  | 540
RDS-200 ¦ NB IP from 9-2E to 2-1E and bridges 9-2E @ CU#2, 1-1E @ ice road, 2-1E @ CU#1 | 2027-09-16 | 2028-01-13 | [5 empty] | 120
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2025-01-29 | 2025-04-28 |  | 90
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2025-04-29 | 2025-12-24 |  |  | 240
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2025-12-25 | 2026-03-24 |  |  |  | 90
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2026-03-25 | 2027-09-15 |  |  |  |  | 540
RDS-201 ¦ SB IP from 6-1W to 9-2W and bridges 6-1W @ CU#1, 1-1W @ ice road, 9-2W @ CU#2 | 2027-09-16 | 2028-01-13 | [5 empty] | 120
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2025-01-29 | 2025-04-28 |  | 90
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2025-04-29 | 2025-12-24 |  |  | 240
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2025-12-25 | 2026-03-24 |  |  |  | 90
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2026-03-25 | 2027-09-15 |  |  |  |  | 540
RDS-202 ¦ IP and Service Roads Partial Rehabilitation Ph 2 | 2027-09-16 | 2028-01-13 | [5 empty] | 120
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2026-01-29 | 2026-04-28 |  | 90
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-204 ¦ NB SR Sta 456+00 to 462+50 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-205 ¦ NB SR Sta 482+00 to 489+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-206 ¦ NB SR Sta 507+50 to 567+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-207 ¦ NB SR Sta 577+00 to 587+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-208 ¦ SB SR Sta 553+00 to 583+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-209 ¦ Sta 551+50 interior recirculating road | 2026-01-29 | 2026-04-28 |  | 90
RDS-209 ¦ Sta 551+50 interior recirculating road | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-209 ¦ Sta 551+50 interior recirculating road | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-209 ¦ Sta 551+50 interior recirculating road | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-209 ¦ Sta 551+50 interior recirculating road | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-210 ¦ Sta 542+00 road to N Express | 2026-01-29 | 2026-04-28 |  | 90
RDS-210 ¦ Sta 542+00 road to N Express | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-210 ¦ Sta 542+00 road to N Express | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-210 ¦ Sta 542+00 road to N Express | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-210 ¦ Sta 542+00 road to N Express | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-211 ¦ Sta 507+00 ice road | 2026-01-29 | 2026-04-28 |  | 90
RDS-211 ¦ Sta 507+00 ice road | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-211 ¦ Sta 507+00 ice road | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-211 ¦ Sta 507+00 ice road | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-211 ¦ Sta 507+00 ice road | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-212 ¦ SB SR Sta 469+00 to 479+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-213 ¦ SB SR Sta 453+00 to Sta 437+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2026-01-29 | 2026-04-28 |  | 90
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-214 ¦ SB SR Sta 331+00 to 405+00 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2026-01-29 | 2026-04-28 |  | 90
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2026-04-29 | 2026-12-24 |  |  | 240
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2026-12-25 | 2027-03-24 |  |  |  | 90
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2027-03-25 | 2028-09-14 |  |  |  |  | 540
RDS-215 ¦ IP and Service Roads Partial Rehabilitation Ph 3 | 2028-09-15 | 2029-01-12 | [5 empty] | 120
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2027-01-29 | 2027-04-28 |  | 90
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2027-04-29 | 2027-12-24 |  |  | 240
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2027-12-25 | 2028-03-23 |  |  |  | 90
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2028-03-24 | 2029-09-14 |  |  |  |  | 540
RDS-216 ¦ IP and Service Roads Partial Rehabilitation Ph 4 | 2029-09-15 | 2030-01-12 | [5 empty] | 120
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2023-10-13 | 2023-12-11 |  | 60
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2023-12-12 | 2024-06-08 |  |  | 180
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2024-06-09 | 2024-09-06 |  |  |  | 90
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2024-09-07 | 2025-09-06 |  |  |  |  | 365
UTL-018 ¦ Rehab Open Storm Channels FY18/19 ($220M pre-approved) | 2025-09-07 | 2025-11-05 | [5 empty] | 60
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2026-10-29 | 2027-06-25 | 240
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2027-06-26 | 2027-08-24 |  | 60
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2027-08-25 | 2028-01-21 |  |  | 150
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2028-01-22 | 2028-04-20 |  |  |  | 90
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2028-04-21 | 2029-07-14 |  |  |  |  | 450
UTL-024-C ¦ High Pole Lighting Replacement (Phase III) | 2029-07-15 | 2029-09-12 | [5 empty] | 60
UTL-043 ¦ Boiler 10 Replacement | 2023-09-14 | 2023-11-12 |  | 60
UTL-043 ¦ Boiler 10 Replacement | 2023-11-13 | 2024-05-10 |  |  | 180
UTL-043 ¦ Boiler 10 Replacement | 2024-05-11 | 2024-08-08 |  |  |  | 90
UTL-043 ¦ Boiler 10 Replacement | 2024-08-09 | 2025-08-03 |  |  |  |  | 360
UTL-043 ¦ Boiler 10 Replacement | 2025-08-04 | 2025-10-02 | [5 empty] | 60
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2032-10-09 | 2032-12-07 |  | 60
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2032-12-08 | 2033-03-07 |  |  | 90
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2033-03-08 | 2033-06-05 |  |  |  | 90
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2033-06-06 | 2033-12-02 |  |  |  |  | 180
UTL-056 ¦ Waste Water - Replace South Foreign Trade Zone Lift Station | 2033-12-03 | 2034-01-31 | [5 empty] | 60
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2033-10-10 | 2033-12-08 |  | 60
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2033-12-09 | 2034-03-08 |  |  | 90
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2034-03-09 | 2034-06-06 |  |  |  | 90
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2034-06-07 | 2034-12-03 |  |  |  |  | 180
UTL-057 ¦ Waste Water - Replace 1W Lift Station | 2034-12-04 | 2035-02-01 | [5 empty] | 60
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2030-04-13 | 2030-06-11 |  | 60
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2030-06-12 | 2030-09-09 |  |  | 90
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2030-09-10 | 2030-12-08 |  |  |  | 90
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2030-12-09 | 2031-09-04 |  |  |  |  | 270
UTL-059 ¦ Waste Water - Reclaimed Water Storage Tank Installation | 2031-09-05 | 2031-11-03 | [5 empty] | 60
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2026-10-09 | 2026-12-07 |  | 60
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2026-12-08 | 2027-03-07 |  |  | 90
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2027-03-08 | 2027-06-05 |  |  |  | 90
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2027-06-06 | 2027-12-02 |  |  |  |  | 180
UTL-060 ¦ Waste Water - Back Up Potable Fill Pipe to Reclaimed Water Tank Installation | 2027-12-03 | 2028-01-31 | [5 empty] | 60
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2032-03-06 | 2032-05-04 |  | 60
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2032-05-05 | 2032-07-03 |  |  | 60
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2032-07-04 | 2032-10-01 |  |  |  | 90
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2032-10-02 | 2032-12-30 |  |  |  |  | 90
UTL-061 ¦ Water - Rehabilitate Elevated Storage Tank | 2032-12-31 | 2033-02-28 | [5 empty] | 60
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2035-01-06 | 2035-03-06 |  | 60
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2035-03-07 | 2035-05-05 |  |  | 60
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2035-05-06 | 2035-08-03 |  |  |  | 90
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2035-08-04 | 2035-11-01 |  |  |  |  | 90
UTL-063 ¦ Waste Water - Reclaimed Water Storage Tank Rehabilitation | 2035-11-02 | 2035-12-31 | [5 empty] | 60
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2027-03-08 | 2027-05-06 |  | 60
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2027-05-07 | 2027-07-05 |  |  | 60
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2027-07-06 | 2027-10-03 |  |  |  | 90
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2027-10-04 | 2028-01-01 |  |  |  |  | 90
UTL-066 ¦ Waste Water - North Commerce Park Lift Station Rehabilitation | 2028-01-02 | 2028-03-01 | [5 empty] | 60
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2023-10-10 | 2023-12-08 |  | 60
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2023-12-09 | 2024-03-07 |  |  | 90
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2024-03-08 | 2024-06-05 |  |  |  | 90
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2024-06-06 | 2024-12-02 |  |  |  |  | 180
UTL-071 ¦ Water - CTA Irrigation Systems Rehabilitation | 2024-12-03 | 2025-01-31 | [5 empty] | 60
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2025-12-12 | 2026-02-09 |  | 60
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2026-02-10 | 2026-05-10 |  |  | 90
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2026-05-11 | 2026-08-08 |  |  |  | 90
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2026-08-09 | 2027-02-04 |  |  |  |  | 180
UTL-074 ¦ Energy Plaza Bridge Crane Rehabilitation | 2027-02-05 | 2027-04-05 | [5 empty] | 60
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2023-10-10 | 2023-12-08 |  | 60
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2023-12-09 | 2024-06-05 |  |  | 180
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2024-06-06 | 2024-09-03 |  |  |  | 90
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2024-09-04 | 2025-08-29 |  |  |  |  | 360
UTL-078 ¦ Thermal - Refurbish 4160 V Switchgear to include Relay and 130VDC Battery Replacements | 2025-08-30 | 2025-10-28 | [5 empty] | 60
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2023-09-14 | 2023-11-12 |  | 60
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2023-11-13 | 2024-05-10 |  |  | 180
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2024-05-11 | 2024-08-08 |  |  |  | 90
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2024-08-09 | 2025-08-03 |  |  |  |  | 360
UTL-088 ¦ Rehabilitate Cooling Towers 2 and 3 | 2025-08-04 | 2025-10-02 | [5 empty] | 60
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2026-12-14 | 2027-02-11 |  | 60
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2027-02-12 | 2027-08-10 |  |  | 180
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2027-08-11 | 2027-11-08 |  |  |  | 90
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2027-11-09 | 2028-11-02 |  |  |  |  | 360
UTL-089 ¦ Thermal - ESP Utility Vault Rehabilitation | 2028-11-03 | 2029-01-01 | [5 empty] | 60
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2030-01-06 | 2030-03-06 |  | 60
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2030-03-07 | 2030-06-04 |  |  | 90
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2030-06-05 | 2030-09-02 |  |  |  | 90
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2030-09-03 | 2031-03-01 |  |  |  |  | 180
UTL-140 ¦ Underground Utility Asset Assessment for Water / Condition Assessment for Water | 2031-03-02 | 2031-06-29 | [5 empty] | 120
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2024-12-09 | 2025-02-06 |  | 60
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2025-02-07 | 2025-05-07 |  |  | 90
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2025-05-08 | 2025-08-05 |  |  |  | 90
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2025-08-06 | 2026-02-01 |  |  |  |  | 180
UTL-143 ¦ Replace Terminal C Lower Roadway Water Mains | 2026-02-02 | 2026-04-02 | [5 empty] | 60
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2023-09-14 | 2023-11-12 |  | 60
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2023-11-13 | 2024-05-10 |  |  | 180
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2024-05-11 | 2024-08-08 |  |  |  | 90
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2024-08-09 | 2025-08-03 |  |  |  |  | 360
UTL-154 ¦ Epoxy Coat OM Chiller End Bells | 2025-08-04 | 2025-10-02 | [5 empty] | 60
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2027-01-09 | 2027-03-09 |  | 60
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2027-03-10 | 2027-06-07 |  |  | 90
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2027-06-08 | 2027-09-05 |  |  |  | 90
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2027-09-06 | 2028-03-03 |  |  |  |  | 180
UTL-155 ¦ Rehabilitate Terminal A Sanitary Sewer Main | 2028-03-04 | 2028-05-02 | [5 empty] | 60
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2026-10-07 | 2026-12-05 |  | 60
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2026-12-06 | 2027-03-05 |  |  | 90
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2027-03-06 | 2027-06-03 |  |  |  | 90
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2027-06-04 | 2027-11-30 |  |  |  |  | 180
UTL-156 ¦ Replace Terminal A Roadway Water Mains | 2027-12-01 | 2028-01-29 | [5 empty] | 60
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2029-10-08 | 2029-12-06 |  | 60
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2029-12-07 | 2030-03-06 |  |  | 90
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2030-03-07 | 2030-06-04 |  |  |  | 90
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2030-06-05 | 2030-12-01 |  |  |  |  | 180
UTL-158 ¦ Rehabilitate Terminal B Sanitary Sewer Main | 2030-12-02 | 2031-01-30 | [5 empty] | 60
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2029-10-05 | 2029-12-03 |  | 60
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2029-12-04 | 2030-03-03 |  |  | 90
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2030-03-04 | 2030-06-01 |  |  |  | 90
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2030-06-02 | 2030-11-28 |  |  |  |  | 180
UTL-160 ¦ Replace Terminal B Roadway Water Mains | 2030-11-29 | 2031-01-27 | [5 empty] | 60
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2029-11-08 | 2030-01-06 |  | 60
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2030-01-07 | 2030-04-06 |  |  | 90
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2030-04-07 | 2030-07-05 |  |  |  | 90
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2030-07-06 | 2030-11-02 |  |  |  |  | 120
UTL-163 ¦ Install Reclaimed Water Main 24 from International to S 20th Street | 2030-11-03 | 2031-03-02 | [5 empty] | 120
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2029-10-09 | 2029-12-07 |  | 60
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2029-12-08 | 2030-03-07 |  |  | 90
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2030-03-08 | 2030-06-05 |  |  |  | 90
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2030-06-06 | 2030-12-02 |  |  |  |  | 180
UTL-180 ¦ Install 16-inch Reclaimed Water main from Passport Drive to East Site Utility Plant | 2030-12-03 | 2031-04-01 | [5 empty] | 120
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2029-12-11 | 2030-02-08 |  | 60
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2030-02-09 | 2030-08-07 |  |  | 180
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2030-08-08 | 2030-11-05 |  |  |  | 90
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2030-11-06 | 2031-10-31 |  |  |  |  | 360
UTL-185 ¦ Thermal - Replace All BTU Metering Devices and Supporting Equipment | 2031-11-01 | 2031-12-30 | [5 empty] | 60
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2026-12-13 | 2027-02-10 |  | 60
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2027-02-11 | 2027-08-09 |  |  | 180
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2027-08-10 | 2027-11-07 |  |  |  | 90
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2027-11-08 | 2028-11-01 |  |  |  |  | 360
UTL-188 ¦ Andover Continuum Control System Rehabilitation or Replacement | 2028-11-02 | 2028-12-31 | [5 empty] | 60
UTL-194 ¦ Other Utility Rehabilitation Projects (Ongoing Assessments) | 2023-06-06 | 2035-09-30 |  |  |  |  | 4500
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2026-10-01 | 2027-05-28 | 240
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2027-05-29 | 2027-07-16 |  | 49
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2027-07-17 | 2028-03-29 |  |  | 257
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2028-03-30 | 2028-07-29 |  |  |  | 122
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2028-07-30 | 2028-11-26 |  |  |  |  | 120
UTL-202 ¦ Energy Plaza Utility Tunnel Rehabilitation | 2028-11-27 | 2029-03-26 | [5 empty] | 120
TF2-003 ¦ Programatic EA-NEPA | 2023-06-06 | 2023-06-06 | 0
TF2-003 ¦ Programatic EA-NEPA | 2023-06-06 | 2023-06-06 |  | 0
TF2-003 ¦ Programatic EA-NEPA | 2023-06-06 | 2023-06-06 |  |  |  | 0
TF2-003 ¦ Programatic EA-NEPA | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
TF2-003 ¦ Programatic EA-NEPA | 2023-06-06 | 2023-06-06 | [5 empty] | 0
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2023-06-06 | 2023-06-06 |  | 0
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2023-06-06 | 2023-06-06 |  |  | 0
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2023-06-06 | 2023-06-06 |  |  |  | 0
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2023-06-06 | 2023-06-06 | [5 empty] | 0
TF2-018-B ¦ Terminal C Renovations | 2023-06-06 | 2023-06-06 | 0
TF2-018-B ¦ Terminal C Renovations | 2023-06-06 | 2023-06-06 |  | 0
TF2-018-B ¦ Terminal C Renovations | 2023-06-06 | 2023-06-06 |  |  |  | 0
TF2-018-B ¦ Terminal C Renovations | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
TF2-018-B ¦ Terminal C Renovations | 2023-06-06 | 2023-06-06 | [5 empty] | 0
TF2-018-B ¦ Confidential Central Option (Planning) | 2023-06-06 | 2023-06-06 |  | 0
TF2-018-B ¦ Confidential Central Option (Planning) | 2023-06-06 | 2023-06-06 |  |  | 0
TF2-018-B ¦ Confidential Central Option (Planning) | 2023-06-06 | 2023-06-06 |  |  |  | 0
TF2-018-B ¦ Confidential Central Option (Planning) | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
TF2-018-B ¦ Confidential Central Option (Planning) | 2023-06-06 | 2023-06-06 | [5 empty] | 0
TF2-018-B ¦ Confidential Central Option (DCC) | 2023-06-06 | 2023-06-06 |  | 0
TF2-018-B ¦ Confidential Central Option (DCC) | 2023-06-06 | 2023-06-06 |  |  | 0
TF2-018-B ¦ Confidential Central Option (DCC) | 2023-06-06 | 2023-06-06 |  |  |  | 0
TF2-018-B ¦ Confidential Central Option (DCC) | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
TF2-018-B ¦ Confidential Central Option (DCC) | 2023-06-06 | 2023-06-06 | [5 empty] | 0
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2023-06-21 | 2023-06-21 |  | 0
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2023-12-02 | 2024-12-25 |  |  | 390
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2024-06-27 | 2027-02-01 |  |  |  |  | 950
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2027-02-02 | 2027-05-02 | [5 empty] | 90
TFF-002 ¦ Terminal E Reconfiguration | 2023-07-31 | 2024-01-07 |  | 161
TFF-002 ¦ Terminal E Reconfiguration | 2024-01-08 | 2024-07-04 |  |  | 179
TFF-002 ¦ Terminal E Reconfiguration | 2023-07-11 | 2024-09-28 |  |  |  | 446
TFF-002 ¦ Terminal E Reconfiguration | 2024-09-29 | 2026-06-30 |  |  |  |  | 640
TFF-002 ¦ Terminal E Reconfiguration | 2026-07-01 | 2026-10-28 | [5 empty] | 120
TFF-003 ¦ Terminal F Civil & Utility | 2024-01-05 | 2024-05-31 |  |  |  | 148
TFF-003 ¦ Terminal F Civil & Utility | 2024-06-01 | 2025-12-27 |  |  |  |  | 575
TFF-003 ¦ Terminal F Civil & Utility | 2025-12-28 | 2026-03-27 | [5 empty] | 90
TFF-004 ¦ BHS, Goods Delivery & Services* | 2024-02-03 | 2024-07-31 |  |  | 180
TFF-004 ¦ BHS, Goods Delivery & Services* | 2023-07-02 | 2024-02-02 |  |  |  | 216
TFF-004 ¦ BHS, Goods Delivery & Services* | 2024-08-01 | 2026-04-26 |  |  |  |  | 634
TFF-004 ¦ BHS, Goods Delivery & Services* | 2026-04-27 | 2026-08-24 | [5 empty] | 120
TFF-005 ¦ Terminal D Bus Station | 2023-06-21 | 2023-06-30 |  | 10
TFF-005 ¦ Terminal D Bus Station | 2023-07-01 | 2024-01-31 |  |  | 215
TFF-005 ¦ Terminal D Bus Station | 2024-01-30 | 2024-07-05 |  |  |  | 158
TFF-005 ¦ Terminal D Bus Station | 2024-07-06 | 2025-01-31 |  |  |  |  | 210
TFF-005 ¦ Terminal D Bus Station | 2025-02-01 | 2025-05-31 | [5 empty] | 120
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2024-01-22 | 2024-05-31 |  |  |  | 131
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2024-06-01 | 2025-05-26 |  |  |  |  | 360
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2025-05-27 | 2025-08-24 | [5 empty] | 90
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2023-06-20 | 2023-08-07 |  | 49
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2023-07-24 | 2024-02-05 |  |  | 197
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2024-02-06 | 2024-08-04 |  |  |  | 181
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2024-08-05 | 2024-12-02 |  |  |  |  | 120
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2024-12-03 | 2025-03-02 | [5 empty] | 90
AFD-048-A ¦ Southwest End-Around Taxiway Project | 2024-01-22 | 2024-03-22 | [5 empty] | 60
AFD-048-D ¦ Southwest End-Around Taxiway Construction (Outter Loop) | 2033-05-01 | 2033-07-29 |  |  |  | 90
AFD-048-D ¦ Southwest End-Around Taxiway Construction (Outter Loop) | 2033-07-30 | 2034-09-23 |  |  |  |  | 421
AFD-048-D ¦ Southwest End-Around Taxiway Construction (Outter Loop) | 2034-09-24 | 2035-01-21 | [5 empty] | 120
AFD-062-A ¦ RWY 17C/35C Reconstruction -Taxiway Mike North (Const. Pkg. - III) | 2023-11-30 | 2024-04-03 |  |  |  | 126
AFD-062-A ¦ RWY 17C/35C Reconstruction -Taxiway Mike North (Const. Pkg. - III) | 2024-04-04 | 2025-01-28 |  |  |  |  | 300
AFD-062-A ¦ RWY 17C/35C Reconstruction -Taxiway Mike North (Const. Pkg. - III) | 2025-01-29 | 2025-05-28 | [5 empty] | 120
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2025-03-13 | 2025-07-10 | [5 empty] | 120
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2023-06-25 | 2023-12-21 | [5 empty] | 180
AFD-141 ¦ Airfield Pavement Remediation | 2023-06-25 | 2023-10-22 | [5 empty] | 120
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2023-12-15 | 2024-02-12 | [5 empty] | 60
AFD-142 ¦ Taxiway G Rehabilitation | 2023-12-28 | 2024-02-14 |  | 49
AFD-142 ¦ Taxiway G Rehabilitation | 2024-01-31 | 2024-10-13 |  |  | 257
AFD-142 ¦ Taxiway G Rehabilitation | 2024-10-20 | 2025-11-30 |  |  |  | 407
AFD-142 ¦ Taxiway G Rehabilitation | 2025-12-01 | 2026-09-06 |  |  |  |  | 280
AFD-142 ¦ Taxiway G Rehabilitation | 2026-09-07 | 2027-01-04 | [5 empty] | 120
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2023-06-06 | 2023-07-05 | 30
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2023-07-06 | 2023-10-15 |  | 102
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2023-10-16 | 2024-10-19 |  |  | 370
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2024-10-20 | 2025-02-19 |  |  |  | 123
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2025-02-20 | 2025-06-20 |  |  |  |  | 121
AFD-147 ¦ Grinding and Grooving of 18L/36R | 2025-06-21 | 2025-12-16 | [5 empty] | 179
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2023-06-06 | 2023-07-05 | 30
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
AFD-149 ¦ SE and E Airfield Lighting Vaults HVAC Rehabilitation | 2024-03-06 | 2024-04-04 | [5 empty] | 30
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2023-06-06 | 2023-07-05 | 30
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
AFD-150 ¦ Airfield Grading and Drainage Rehabilitation | 2024-03-06 | 2024-04-04 | [5 empty] | 30
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2023-07-21 | 2023-08-09 |  | 20
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2023-08-10 | 2023-09-23 |  |  | 45
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2023-09-24 | 2023-09-24 |  |  |  | 0
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2023-09-25 | 2024-01-22 |  |  |  |  | 120
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2024-01-23 | 2024-03-27 | [5 empty] | 65
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2023-08-09 | 2023-09-28 |  |  |  | 51
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2023-10-01 | 2025-04-30 |  |  |  |  | 578
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2025-07-01 | 2025-08-30 | [5 empty] | 61
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2023-11-23 | 2024-03-21 | [5 empty] | 120
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2024-01-03 | 2024-03-02 | [5 empty] | 60
TF2-002 ¦ Supplementary CUP (eCUP) | 2025-02-28 | 2025-06-28 | [5 empty] | 121
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2025-03-22 | 2025-05-20 | [5 empty] | 60
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2024-08-11 | 2024-11-04 | [5 empty] | 86
TFD-003 ¦ CTA Expansion - C Pier | 2023-12-06 | 2023-12-06 |  |  |  | 0
TFD-003 ¦ CTA Expansion - C Pier | 2024-01-01 | 2026-01-18 |  |  |  |  | 749
TFD-003 ¦ CTA Expansion - C Pier | 2026-01-19 | 2026-04-18 | [5 empty] | 90
TFD-004 ¦ CTA Expansion - A Pier | 2023-09-01 | 2023-09-01 |  |  |  | 0
TFD-004 ¦ CTA Expansion - A Pier | 2024-03-01 | 2026-04-30 |  |  |  |  | 791
TFD-004 ¦ CTA Expansion - A Pier | 2026-05-01 | 2026-07-29 | [5 empty] | 90
TFD-005 ¦ Terminal C Renovation Phase 1 | 2024-02-01 | 2024-02-01 |  |  |  | 0
TFD-005 ¦ Terminal C Renovation Phase 1 | 2024-02-01 | 2026-01-21 |  |  |  |  | 721
TFD-005 ¦ Terminal C Renovation Phase 1 | 2026-01-22 | 2026-04-21 | [5 empty] | 90
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2025-11-11 | 2028-12-20 |  |  |  |  | 1136
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2028-12-21 | 2029-04-19 | [5 empty] | 120
TFD-007 ¦ CTA Exp-Term C Garage South | 2023-08-28 | 2024-01-07 |  |  |  | 133
TFD-007 ¦ CTA Exp-Term C Garage South | 2024-01-08 | 2028-05-06 |  |  |  |  | 1581
TFD-007 ¦ CTA Exp-Term C Garage South | 2028-05-07 | 2028-08-04 | [5 empty] | 90
TFD-008 ¦ CTA Exp-Utility Corr | 2023-07-10 | 2025-04-09 |  |  |  |  | 640
TFD-008 ¦ CTA Exp-Utility Corr | 2025-04-10 | 2025-07-08 | [5 empty] | 90
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2024-04-01 | 2024-11-25 |  |  | 239
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2024-08-31 | 2025-02-02 |  |  |  | 156
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2025-02-03 | 2025-08-31 |  |  |  |  | 210
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2025-09-01 | 2026-02-27 | [5 empty] | 180
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2023-12-01 | 2023-12-01 |  |  |  | 0
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2024-03-11 | 2026-04-30 |  |  |  |  | 781
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2026-05-01 | 2026-11-27 | [5 empty] | 211
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2023-12-23 | 2024-03-29 | [5 empty] | 98
ENV-011 ¦ Remote Bus Fleet Electrification | 2023-06-06 | 2023-07-05 | 30
ENV-011 ¦ Remote Bus Fleet Electrification | 2023-07-06 | 2023-08-04 |  | 30
ENV-011 ¦ Remote Bus Fleet Electrification | 2023-08-05 | 2023-09-03 |  |  | 30
ENV-011 ¦ Remote Bus Fleet Electrification | 2023-09-04 | 2023-10-03 |  |  |  | 30
ENV-011 ¦ Remote Bus Fleet Electrification | 2023-10-04 | 2024-12-30 |  |  |  |  | 454
ENV-011 ¦ Remote Bus Fleet Electrification | 2024-12-31 | 2025-01-29 | [5 empty] | 30
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2030-10-07 | 2031-01-04 |  |  |  | 90
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2031-01-05 | 2031-01-09 |  |  |  |  | 5
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2031-01-10 | 2031-05-09 | [5 empty] | 120
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2026-03-14 | 2026-11-08 | 240
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2026-11-09 | 2027-01-02 |  | 55
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2027-01-03 | 2027-05-29 |  |  | 147
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2027-05-30 | 2027-08-27 |  |  |  | 90
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2027-08-28 | 2028-08-26 |  |  |  |  | 365
OTH-026-E ¦ First Flush Storm Water Pipeline Realignment at planned Southwest Campus. | 2028-08-27 | 2028-12-24 | [5 empty] | 120
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2023-07-24 | 2024-04-18 |  |  |  |  | 270
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2024-04-19 | 2024-08-16 | [5 empty] | 120
OTH-076 ¦ East Material Management Site | 2024-03-28 | 2024-06-26 |  |  |  |  | 91
OTH-076 ¦ East Material Management Site | 2029-02-25 | 2029-04-25 | [5 empty] | 60
OTH-081 ¦ Materials Testing Lab | 2023-07-18 | 2023-07-18 |  |  | 0
OTH-081 ¦ Materials Testing Lab | 2023-07-18 | 2024-03-27 |  |  |  | 254
OTH-081 ¦ Materials Testing Lab | 2024-03-28 | 2024-09-23 |  |  |  |  | 180
OTH-081 ¦ Materials Testing Lab | 2024-09-24 | 2025-01-21 | [5 empty] | 120
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2023-10-27 | 2024-01-24 | [5 empty] | 90
OTH-091 ¦ DCC Elevated Walkways Replacement | 2024-02-03 | 2024-05-22 |  |  |  | 110
OTH-091 ¦ DCC Elevated Walkways Replacement | 2024-05-23 | 2024-12-18 |  |  |  |  | 210
OTH-091 ¦ DCC Elevated Walkways Replacement | 2024-12-19 | 2025-03-25 | [5 empty] | 97
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2023-06-06 | 2023-07-05 | 30
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2023-07-06 | 2023-08-04 |  | 30
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2023-08-05 | 2023-09-03 |  |  | 30
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2023-09-04 | 2023-10-03 |  |  |  | 30
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
OTH-100 ¦ Ground Transportation Administration Building Renovation | 2024-03-06 | 2024-04-04 | [5 empty] | 30
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2024-07-06 | 2024-10-15 |  | 102
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2024-10-16 | 2025-10-20 |  |  | 370
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2025-10-21 | 2026-02-20 |  |  |  | 123
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2026-02-26 | 2026-06-26 |  |  |  |  | 121
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2026-06-27 | 2026-12-23 | [5 empty] | 180
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2024-02-18 | 2024-05-25 |  |  |  | 98
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2024-05-26 | 2025-05-21 |  |  |  |  | 361
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2025-05-22 | 2025-09-18 | [5 empty] | 120
RDS-007 ¦ East West Connector Roadway | 2023-07-08 | 2025-05-13 |  |  |  |  | 676
RDS-007 ¦ East West Connector Roadway | 2025-05-14 | 2025-09-10 | [5 empty] | 120
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2023-06-06 | 2023-09-13 | 100
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2023-09-14 | 2023-11-12 |  | 60
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2023-11-13 | 2024-11-11 |  |  | 365
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2024-11-12 | 2025-02-09 |  |  |  | 90
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2025-02-10 | 2029-01-19 |  |  |  |  | 1440
RDS-018 ¦ Landside Roads & Bridges Rehabilitation Phase 4d | 2029-01-20 | 2029-03-20 | [5 empty] | 60
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2023-06-06 | 2023-09-13 | 100
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2023-09-14 | 2023-11-12 |  | 60
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2023-11-13 | 2024-08-08 |  |  | 270
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2024-08-09 | 2024-11-06 |  |  |  | 90
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2024-11-07 | 2025-11-06 |  |  |  |  | 365
RDS-019 ¦ Landside Roads & Bridges Rehabilitation Phase 3a | 2025-11-07 | 2026-03-06 | [5 empty] | 120
RDS-025 ¦ Cloverleafs & Ramps North Airfield Drive Bridge | 2023-12-10 | 2026-07-05 |  |  |  |  | 939
RDS-025 ¦ Cloverleafs & Ramps North Airfield Drive Bridge | 2026-07-06 | 2027-01-01 | [5 empty] | 180
RDS-029-B ¦ Glade Road and Bridge Replacement | 2023-06-24 | 2023-10-21 | [5 empty] | 120
RDS-050-A ¦ Skylink Structural Improvements | 2024-09-14 | 2025-01-12 | [5 empty] | 121
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2023-06-26 | 2023-11-23 |  |  |  |  | 151
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2023-11-24 | 2024-03-22 | [5 empty] | 120
RDS-067-A ¦ Replacement of 2 Flyover Bridges to Terminals A & E | 2024-07-04 | 2024-10-31 | [5 empty] | 120
RDS-067-A ¦ Replacement of 2 Flyover Bridges to Terminals A & E | 2024-07-04 | 2024-10-31 | [5 empty] | 120
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2023-12-11 | 2026-07-05 |  |  |  |  | 938
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2026-07-06 | 2027-01-01 | [5 empty] | 180
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2023-09-18 | 2024-01-15 | [5 empty] | 120
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2024-04-03 | 2024-07-13 |  | 102
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2024-07-14 | 2025-07-18 |  |  | 370
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2025-07-19 | 2025-11-26 |  |  |  | 131
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2025-11-27 | 2026-03-27 |  |  |  |  | 121
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2026-03-28 | 2026-09-23 | [5 empty] | 180
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 | 0
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 |  | 0
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 |  |  | 0
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 |  |  |  | 0
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
RDS-193 ¦ Arterial Roads Rehab and Reconstruct Phase 1 | 2023-06-06 | 2023-06-06 | [5 empty] | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 |  | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 |  |  | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 |  |  |  | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 |  |  |  |  | 0
RDS-203 ¦ NB Service Road | 2023-06-06 | 2023-06-06 | [5 empty] | 0
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2023-07-31 | 2023-09-17 |  | 49
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2023-09-18 | 2024-08-15 |  |  | 333
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2024-08-16 | 2024-12-25 |  |  |  | 132
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2024-12-26 | 2026-10-16 |  |  |  |  | 660
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2026-10-17 | 2027-02-13 | [5 empty] | 120
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2023-06-06 | 2023-07-05 | 30
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2023-07-06 | 2023-08-04 |  | 30
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2023-08-05 | 2023-09-03 |  |  | 30
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2023-09-04 | 2023-10-03 |  |  |  | 30
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
RDS-218 ¦ Guardrail and Attenuator Replacement Project | 2024-03-06 | 2024-04-04 | [5 empty] | 30
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2023-06-06 | 2023-07-05 | 30
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2023-07-06 | 2023-08-04 |  | 30
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2023-08-05 | 2023-09-03 |  |  | 30
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2023-09-04 | 2023-10-03 |  |  |  | 30
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2023-10-04 | 2024-05-07 |  |  |  |  | 217
RDS-220 ¦ IP Main Lanes Rehabilitation Asphalt Overlay | 2024-05-08 | 2024-06-06 | [5 empty] | 30
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-01-01 | 2032-04-06 | 97
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-04-07 | 2032-04-07 |  | 0
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-04-07 | 2032-04-07 |  |  | 0
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-04-07 | 2032-04-07 |  |  |  | 0
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-04-07 | 2032-04-07 |  |  |  |  | 0
TER-293 ¦ Terminal D Pet Relief Area Upgrade | 2032-04-07 | 2032-04-07 | [5 empty] | 0
UTL-004-B ¦ Landside Storm Sewer Repair | 2023-07-11 | 2023-11-07 | [5 empty] | 120
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2023-12-10 | 2026-07-05 |  |  |  |  | 939
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2026-07-06 | 2027-01-01 | [5 empty] | 180
UTL-031 ¦ Conveyance Replacement (Others) | 2030-07-01 | 2030-10-08 | 100
UTL-031 ¦ Conveyance Replacement (Others) | 2030-10-09 | 2030-12-07 |  | 60
UTL-031 ¦ Conveyance Replacement (Others) | 2030-12-08 | 2031-03-07 |  |  | 90
UTL-031 ¦ Conveyance Replacement (Others) | 2031-03-08 | 2031-05-01 |  |  |  | 55
UTL-031 ¦ Conveyance Replacement (Others) | 2031-05-02 | 2031-08-09 |  |  |  |  | 100
UTL-031 ¦ Conveyance Replacement (Others) | 2031-08-10 | 2031-10-08 | [5 empty] | 60
UTL-045 ¦ East & West Potable Water Pump Stations | 2023-10-09 | 2024-10-07 |  |  |  |  | 365
UTL-045 ¦ East & West Potable Water Pump Stations | 2024-11-17 | 2025-05-15 | [5 empty] | 180
UTL-161 ¦ 1W Lift Station at North Express Parking | 2023-06-06 | 2024-01-31 | 240
UTL-161 ¦ 1W Lift Station at North Express Parking | 2024-02-01 | 2024-03-31 |  | 60
UTL-161 ¦ 1W Lift Station at North Express Parking | 2024-04-01 | 2024-06-29 |  |  | 90
UTL-161 ¦ 1W Lift Station at North Express Parking | 2024-06-30 | 2024-09-27 |  |  |  | 90
UTL-161 ¦ 1W Lift Station at North Express Parking | 2024-09-28 | 2025-03-26 |  |  |  |  | 180
UTL-161 ¦ 1W Lift Station at North Express Parking | 2025-03-27 | 2025-05-25 | [5 empty] | 60
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2023-09-27 | 2024-01-24 |  |  |  | 120
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2024-01-25 | 2024-06-12 |  |  |  |  | 140
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2024-06-13 | 2024-10-10 | [5 empty] | 120
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2024-06-04 | 2024-09-30 | 119
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2024-10-01 | 2024-12-29 |  | 90
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2024-12-30 | 2025-12-24 |  |  | 360
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2025-12-25 | 2026-03-24 |  |  |  | 90
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2026-03-25 | 2027-09-15 |  |  |  |  | 540
UTL-208 ¦ Above Ground Storage Tanks at P&G | 2027-09-16 | 2028-01-13 | [5 empty] | 120
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2023-06-06 | 2023-07-05 | 30
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2023-07-06 | 2023-08-04 |  | 30
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2023-08-05 | 2023-10-03 |  |  | 60
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2023-10-04 | 2023-11-02 |  |  |  | 30
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2023-11-03 | 2024-04-30 |  |  |  |  | 180
UTL-218 ¦ Energy Plaza - Rehabilitate and Convert York Titan OM Chillers | 2024-05-01 | 2024-05-30 | [5 empty] | 30
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2024-03-16 | 2024-05-17 |  | 63
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2024-05-18 | 2025-03-02 |  |  | 289
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2025-03-03 | 2025-07-09 |  |  |  | 129
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2025-07-10 | 2026-03-17 |  |  |  |  | 251
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2026-03-18 | 2026-10-13 | [5 empty] | 210
NOTH-098 ¦ RCC Interior Lighting Design | 2023-06-06 | 2023-07-05 | 30
NOTH-098 ¦ RCC Interior Lighting Design | 2023-07-06 | 2023-08-04 |  | 30
NOTH-098 ¦ RCC Interior Lighting Design | 2023-08-05 | 2023-09-03 |  |  | 30
NOTH-098 ¦ RCC Interior Lighting Design | 2023-09-04 | 2023-10-03 |  |  |  | 30
NOTH-098 ¦ RCC Interior Lighting Design | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
NOTH-098 ¦ RCC Interior Lighting Design | 2024-03-06 | 2024-04-04 | [5 empty] | 30
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2023-06-06 | 2023-07-05 | 30
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2023-07-06 | 2023-08-04 |  | 30
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2023-08-05 | 2023-09-03 |  |  | 30
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2023-09-04 | 2023-10-03 |  |  |  | 30
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
NUTL-219 ¦ RCC Bus Maintenance and Fueling Facility HVAC Rehab | 2024-03-06 | 2024-04-04 | [5 empty] | 30
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2023-06-06 | 2023-07-05 | 30
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
OTH-097 ¦ Terminal B Parking Garage Rehabilitation | 2024-03-06 | 2024-04-04 | [5 empty] | 30
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2023-06-06 | 2023-07-05 | 30
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2023-07-06 | 2023-08-04 |  | 30
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2023-08-05 | 2023-09-03 |  |  | 30
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2023-09-04 | 2023-10-03 |  |  |  | 30
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
OTH-099 ¦ Salvage Yard Warehouse Buildings | 2024-03-06 | 2024-04-04 | [5 empty] | 30
OTH-101 ¦ The Catalyst Center | 2023-06-06 | 2023-07-05 | 30
OTH-101 ¦ The Catalyst Center | 2023-07-06 | 2023-08-04 |  | 30
OTH-101 ¦ The Catalyst Center | 2023-08-05 | 2023-09-03 |  |  | 30
OTH-101 ¦ The Catalyst Center | 2023-09-04 | 2023-10-03 |  |  |  | 30
OTH-101 ¦ The Catalyst Center | 2023-10-04 | 2024-01-11 |  |  |  |  | 100
OTH-101 ¦ The Catalyst Center | 2024-01-12 | 2024-02-10 | [5 empty] | 30
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2023-06-06 | 2023-07-05 | 30
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2023-07-06 | 2023-08-04 |  | 30
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2023-08-05 | 2023-09-03 |  |  | 30
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2023-09-04 | 2023-10-03 |  |  |  | 30
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2023-10-04 | 2024-03-08 |  |  |  |  | 157
SAF-097 ¦ Terminal Exit Lane Program - Phase 1 | 2024-03-09 | 2024-04-07 | [5 empty] | 30
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2023-06-06 | 2023-07-05 | 30
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2023-07-06 | 2023-08-04 |  | 30
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2023-08-05 | 2023-09-03 |  |  | 30
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2023-09-04 | 2023-10-03 |  |  |  | 30
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
TER-305 ¦ Terminal Golf Carts - Parking Locations | 2024-03-06 | 2024-04-04 | [5 empty] | 30
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2023-06-06 | 2023-07-05 | 30
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2023-10-04 | 2024-03-05 |  |  |  |  | 154
TER-306 ¦ Terminal B Back of House Restrooms Lift Station Rehabilitation | 2024-03-06 | 2024-04-04 | [5 empty] | 30
TER-307 ¦ CBP - BIDS | 2023-06-06 | 2023-07-05 | 30
TER-307 ¦ CBP - BIDS | 2023-07-06 | 2023-08-04 |  | 30
TER-307 ¦ CBP - BIDS | 2023-08-05 | 2023-09-03 |  |  | 30
TER-307 ¦ CBP - BIDS | 2023-09-04 | 2023-10-03 |  |  |  | 30
TER-307 ¦ CBP - BIDS | 2023-10-04 | 2024-01-11 |  |  |  |  | 100
TER-307 ¦ CBP - BIDS | 2024-01-12 | 2024-02-10 | [5 empty] | 30
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2025-03-03 | 2025-03-03 |  |  |  | 0
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2023-06-06 | 2024-01-31 | 240
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2024-02-01 | 2024-03-31 |  | 60
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2024-04-01 | 2024-09-27 |  |  | 180
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2024-09-28 | 2024-12-26 |  |  |  | 90
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2024-12-27 | 2025-12-21 |  |  |  |  | 360
UTL-189 ¦ Terminal D HVAC, Smoke Evac, and BAS Rehabilitation | 2025-12-22 | 2026-02-19 | [5 empty] | 60
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2023-06-06 | 2023-07-05 | 30
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2023-07-06 | 2023-08-04 |  | 30
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2023-08-05 | 2023-09-03 |  |  | 30
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2023-09-04 | 2023-10-03 |  |  |  | 30
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2023-10-04 | 2024-03-01 |  |  |  |  | 150
UTL-210 ¦ Energy Plaza - Replace Sodium Hypochlorite Generation System | 2024-03-02 | 2024-03-31 | [5 empty] | 30
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2023-06-06 | 2023-07-05 | 30
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2023-10-04 | 2024-01-01 |  |  |  |  | 90
UTL-212 ¦ North and South Control Plazas and Remote Parking BAS and HVAC Rehabilitation | 2024-01-02 | 2024-01-31 | [5 empty] | 30
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2023-06-06 | 2023-07-05 | 30
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2023-07-06 | 2023-08-04 |  | 30
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2023-08-05 | 2023-09-03 |  |  | 30
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2023-09-04 | 2023-10-03 |  |  |  | 30
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2023-10-04 | 2024-01-01 |  |  |  |  | 90
UTL-213 ¦ RAC and AHQ BAS and HVAC Rehabilitation | 2024-01-02 | 2024-01-31 | [5 empty] | 30
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2023-06-06 | 2023-08-04 | 60
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2023-08-05 | 2023-10-03 |  | 60
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2023-10-04 | 2023-12-02 |  |  | 60
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2023-12-03 | 2024-01-31 |  |  |  | 60
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2024-02-01 | 2025-04-02 |  |  |  |  | 427
UTL-214 ¦ Procurement Office-Warehouse BLDG HVAC Replacement | 2025-04-03 | 2025-06-01 | [5 empty] | 60
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2023-06-06 | 2023-07-05 | 30
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2023-07-06 | 2023-08-04 |  | 30
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2023-08-05 | 2023-09-03 |  |  | 30
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2023-09-04 | 2023-10-03 |  |  |  | 30
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2023-10-04 | 2024-03-01 |  |  |  |  | 150
UTL-215 ¦ Energy Plaza - Rehabilitate PCA Chiller Controls | 2024-03-02 | 2024-03-31 | [5 empty] | 30
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2023-06-06 | 2023-08-04 | 60
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2023-08-05 | 2023-10-03 |  | 60
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2023-10-04 | 2023-12-02 |  |  | 60
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2023-12-03 | 2024-01-31 |  |  |  | 60
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2024-02-01 | 2024-07-29 |  |  |  |  | 180
UTL-216 ¦ Energy Plaza - Replace Cooling Tower Cell Condenser Water Piping | 2024-07-30 | 2024-09-27 | [5 empty] | 60
AFD-040 ¦ Snow & Ice Vehicle Storage Facility | 2024-04-04 | 2024-10-18 |  |  |  |  | 198
AFD-040 ¦ Snow & Ice Vehicle Storage Facility | 2024-10-19 | 2025-02-15 | [5 empty] | 120
NOTH-020 ¦ RAC Elevator Modular Modernization | 2023-07-09 | 2023-12-16 |  |  |  | 161
NOTH-020 ¦ RAC Elevator Modular Modernization | 2023-12-17 | 2024-10-12 |  |  |  |  | 301
NOTH-020 ¦ RAC Elevator Modular Modernization | 2024-10-13 | 2025-02-09 | [5 empty] | 120
NOTH-075 ¦ Rental Car Center - Restroom Renovations Phase II | 2023-12-11 | 2024-04-08 | [5 empty] | 120
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2023-07-15 | 2024-02-08 |  |  | 209
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2024-02-09 | 2024-05-12 |  |  |  | 94
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2024-05-13 | 2024-11-08 |  |  |  |  | 180
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2024-11-09 | 2025-03-08 | [5 empty] | 120
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2023-07-21 | 2023-09-14 |  | 56
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2023-09-15 | 2024-04-01 |  |  | 200
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2024-04-02 | 2024-08-21 |  |  |  | 142
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2024-08-22 | 2025-01-03 |  |  |  |  | 135
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2025-01-04 | 2025-07-02 | [5 empty] | 180
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2023-06-13 | 2026-02-10 |  |  |  |  | 974
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2026-02-11 | 2026-08-09 | [5 empty] | 180
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-08-03 | 2023-08-03 |  | 1
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-08-04 | 2023-08-26 |  |  | 23
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-08-27 | 2023-10-04 |  |  |  | 39
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-10-05 | 2023-10-25 |  |  |  |  | 21
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-10-26 | 2024-04-22 | [5 empty] | 180
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2023-09-28 | 2023-10-11 |  |  |  | 14
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2023-10-12 | 2023-12-10 |  |  |  |  | 60
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2023-12-11 | 2024-04-08 | [5 empty] | 120
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2023-06-19 | 2024-03-15 |  |  |  |  | 271
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2024-03-16 | 2024-09-11 | [5 empty] | 180
OTH-068 ¦ Smart Flower Solar Installation | 2026-04-07 | 2026-06-15 |  |  | 70
OTH-068 ¦ Smart Flower Solar Installation | 2026-06-16 | 2026-07-06 |  |  |  | 21
OTH-068 ¦ Smart Flower Solar Installation | 2026-07-07 | 2026-08-19 |  |  |  |  | 44
OTH-068 ¦ Smart Flower Solar Installation | 2026-08-20 | 2026-12-17 | [5 empty] | 120
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2023-09-16 | 2024-03-13 | [5 empty] | 180
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2024-06-18 | 2025-01-06 |  |  |  | 203
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2025-01-07 | 2025-09-04 |  |  |  |  | 241
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2025-09-05 | 2026-03-03 | [5 empty] | 180
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2024-02-19 | 2024-08-17 |  |  |  |  | 181
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2024-08-18 | 2024-12-15 | [5 empty] | 120
OTH-086 ¦ Old Conveyances Replacement | 2023-07-11 | 2024-04-27 |  |  | 292
OTH-086 ¦ Old Conveyances Replacement | 2024-04-28 | 2024-08-28 |  |  |  | 123
OTH-086 ¦ Old Conveyances Replacement | 2024-08-29 | 2026-06-03 |  |  |  |  | 644
OTH-086 ¦ Old Conveyances Replacement | 2026-06-04 | 2026-10-01 | [5 empty] | 120
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2023-07-24 | 2023-11-02 |  | 102
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2023-11-03 | 2024-07-14 |  |  | 255
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2024-07-15 | 2024-12-24 |  |  |  | 163
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2025-01-13 | 2025-05-13 |  |  |  |  | 121
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2025-05-14 | 2025-11-09 | [5 empty] | 180
OTH-093 ¦ Parking Customer Service Room Expansion | 2023-06-20 | 2023-08-13 |  |  | 55
OTH-093 ¦ Parking Customer Service Room Expansion | 2023-08-14 | 2023-09-22 |  |  |  | 40
OTH-093 ¦ Parking Customer Service Room Expansion | 2023-09-23 | 2023-12-22 |  |  |  |  | 91
OTH-093 ¦ Parking Customer Service Room Expansion | 2023-12-23 | 2024-04-20 | [5 empty] | 120
RDS-001 ¦ Skylink ATC Replacement | 2023-11-08 | 2024-04-16 | [5 empty] | 161
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2024-04-30 | 2024-08-09 |  | 102
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2024-08-10 | 2025-08-14 |  |  | 370
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2025-08-15 | 2025-12-24 |  |  |  | 132
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2025-12-25 | 2026-04-24 |  |  |  |  | 121
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2026-04-25 | 2026-10-21 | [5 empty] | 180
SAF-012 ¦ DPS Police Outdoor Range Upgrade | 2024-01-01 | 2024-02-29 | [5 empty] | 60
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2023-09-02 | 2024-02-05 |  |  |  | 157
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2024-02-06 | 2025-09-05 |  |  |  |  | 578
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2025-09-06 | 2026-01-03 | [5 empty] | 120
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2023-08-27 | 2023-12-20 |  |  |  | 116
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2023-12-21 | 2024-12-19 |  |  |  |  | 365
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2024-12-20 | 2025-04-18 | [5 empty] | 120
SAF-078 ¦ Employee Inspection Portal Redesign | 2024-01-23 | 2024-09-18 | [5 empty] | 240
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2023-08-22 | 2023-10-09 |  | 49
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2023-10-16 | 2024-06-05 |  |  | 234
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2024-06-06 | 2024-12-05 |  |  |  | 183
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2024-12-06 | 2025-09-30 |  |  |  |  | 299
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2025-10-01 | 2026-01-28 | [5 empty] | 120
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2023-07-13 | 2023-08-30 |  | 49
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2023-08-31 | 2024-03-18 |  |  | 201
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2024-03-19 | 2024-07-05 |  |  |  | 109
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2024-07-06 | 2025-03-09 |  |  |  |  | 247
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2025-03-10 | 2025-07-07 | [5 empty] | 120
TECH-102 ¦ Replacement AACS (RAACS) Program | 2023-06-26 | 2024-03-27 |  |  | 276
TECH-102 ¦ Replacement AACS (RAACS) Program | 2024-03-28 | 2024-03-28 |  |  |  | 0
TECH-102 ¦ Replacement AACS (RAACS) Program | 2024-06-27 | 2027-01-21 |  |  |  |  | 939
TECH-102 ¦ Replacement AACS (RAACS) Program | 2027-01-22 | 2027-06-21 | [5 empty] | 151
TER-067 ¦ Term-A Roofing Project | 2024-10-21 | 2025-03-08 | [5 empty] | 139
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2025-08-22 | 2026-02-17 | [5 empty] | 180
TER-180-A ¦ CTX Replacement Project - Terminal D | 2026-03-14 | 2026-09-09 | [5 empty] | 180
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2023-08-04 | 2024-02-27 |  |  | 207
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2024-03-06 | 2024-09-21 |  |  |  | 199
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2024-09-22 | 2025-03-20 |  |  |  |  | 180
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2025-03-21 | 2025-08-17 | [5 empty] | 150
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2023-06-26 | 2024-02-09 |  |  | 229
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2023-06-06 | 2023-06-06 |  |  |  | 0
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2023-12-22 | 2024-07-18 |  |  |  |  | 210
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2024-07-19 | 2024-09-16 | [5 empty] | 60
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2023-06-29 | 2024-01-16 |  |  |  | 202
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2024-01-17 | 2025-06-16 |  |  |  |  | 517
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2025-06-17 | 2025-08-15 | [5 empty] | 60
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2023-10-27 | 2024-02-12 |  | 109
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2024-08-26 | 2024-12-25 |  |  |  | 122
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2024-12-26 | 2025-04-25 |  |  |  |  | 121
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2025-04-26 | 2025-10-22 | [5 empty] | 180
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2023-12-01 | 2024-05-13 |  |  |  |  | 165
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2024-05-14 | 2024-09-10 | [5 empty] | 120
TER-253 ¦ Terminal Dynamic Glass | 2023-10-03 | 2023-11-20 |  | 49
TER-253 ¦ Terminal Dynamic Glass | 2023-11-21 | 2024-06-04 |  |  | 197
TER-253 ¦ Terminal Dynamic Glass | 2024-06-05 | 2024-08-02 |  |  |  | 59
TER-253 ¦ Terminal Dynamic Glass | 2024-08-04 | 2025-08-19 |  |  |  |  | 381
TER-253 ¦ Terminal Dynamic Glass | 2025-08-20 | 2025-12-17 | [5 empty] | 120
TER-256 ¦ Rental Car Center Garage Reallocation | 2024-06-07 | 2024-10-30 |  |  |  | 146
TER-256 ¦ Rental Car Center Garage Reallocation | 2024-10-31 | 2025-02-27 |  |  |  |  | 120
TER-256 ¦ Rental Car Center Garage Reallocation | 2025-02-28 | 2025-06-27 | [5 empty] | 120
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2023-07-01 | 2023-12-27 | [5 empty] | 180
TER-271 ¦ Terminal D Roofing Project Phase I | 2026-04-19 | 2026-10-05 |  |  |  | 170
TER-271 ¦ Terminal D Roofing Project Phase I | 2026-10-06 | 2028-04-07 |  |  |  |  | 550
TER-271 ¦ Terminal D Roofing Project Phase I | 2028-04-08 | 2028-08-05 | [5 empty] | 120
TER-273 ¦ Sky-link Restrooms Initiative | 2023-12-14 | 2024-04-11 | [5 empty] | 120
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2023-10-22 | 2024-03-31 |  |  |  | 162
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2024-04-01 | 2025-03-02 |  |  |  |  | 336
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2025-03-03 | 2025-07-30 | [5 empty] | 150
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2023-09-24 | 2024-09-22 |  |  |  |  | 365
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2024-09-23 | 2025-02-19 | [5 empty] | 150
TER-287 ¦ Skybridge A-B Conveyances | 2024-06-09 | 2025-11-12 |  |  |  |  | 522
TER-287 ¦ Skybridge A-B Conveyances | 2025-11-13 | 2026-03-12 | [5 empty] | 120
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2023-09-14 | 2023-12-27 |  |  |  | 105
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2023-12-28 | 2025-03-21 |  |  |  |  | 450
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2025-03-22 | 2025-07-19 | [5 empty] | 120
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2026-02-01 | 2026-07-02 |  |  |  | 152
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2026-07-03 | 2027-07-03 |  |  |  |  | 366
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2027-07-04 | 2027-10-31 | [5 empty] | 120
TER-297 ¦ Term-D Sewer Lift Station | 2023-08-20 | 2023-11-17 | [5 empty] | 90
TER-301 ¦ Skylink Elevator Replacement Project | 2023-11-11 | 2024-03-27 |  |  |  | 138
TER-301 ¦ Skylink Elevator Replacement Project | 2024-03-28 | 2027-04-01 |  |  |  |  | 1100
TER-301 ¦ Skylink Elevator Replacement Project | 2027-04-02 | 2027-07-30 | [5 empty] | 120
TER-308 ¦ Skylink Platform Displays Replacement | 2023-10-13 | 2023-10-19 |  | 7
TER-308 ¦ Skylink Platform Displays Replacement | 2023-10-20 | 2024-07-13 |  |  | 268
TER-308 ¦ Skylink Platform Displays Replacement | 2024-07-14 | 2024-12-11 |  |  |  | 151
TER-308 ¦ Skylink Platform Displays Replacement | 2024-12-12 | 2025-10-07 |  |  |  |  | 300
TER-308 ¦ Skylink Platform Displays Replacement | 2025-10-08 | 2026-04-05 | [5 empty] | 180
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2024-03-16 | 2024-05-17 |  | 63
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2024-05-18 | 2025-03-02 |  |  | 289
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2025-07-10 | 2026-03-17 |  |  |  |  | 251
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2026-03-18 | 2026-10-13 | [5 empty] | 210
TRIP-09 ¦ TRIP - Terminal A Pet Conveyor | 2030-10-22 | 2030-12-09 |  |  |  | 49
TRIP-09 ¦ TRIP - Terminal A Pet Conveyor | 2030-12-10 | 2031-03-09 |  |  |  |  | 90
TRIP-09 ¦ TRIP - Terminal A Pet Conveyor | 2031-03-10 | 2031-07-07 | [5 empty] | 120
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2024-02-22 | 2024-04-10 |  | 49
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2024-04-11 | 2024-10-15 |  |  | 188
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2024-10-16 | 2025-02-26 |  |  |  | 134
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2025-02-27 | 2026-08-14 |  |  |  |  | 534
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2026-08-15 | 2026-12-12 | [5 empty] | 120
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2023-07-22 | 2023-10-18 |  |  |  | 89
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2023-10-19 | 2024-06-27 |  |  |  |  | 253
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2024-06-28 | 2024-10-25 | [5 empty] | 120
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2023-07-20 | 2023-11-16 | [5 empty] | 120
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2023-06-06 | 2023-09-28 |  |  | 115
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2023-09-29 | 2024-02-14 |  |  |  | 139
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2024-02-15 | 2024-09-11 |  |  |  |  | 210
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2024-09-13 | 2025-02-09 | [5 empty] | 150
UTL-209 ¦ Trigg Lake Pump Station | 2023-06-20 | 2024-03-29 | 284
UTL-209 ¦ Trigg Lake Pump Station | 2024-03-30 | 2024-07-02 |  | 95
UTL-209 ¦ Trigg Lake Pump Station | 2024-07-03 | 2025-06-17 |  |  | 350
UTL-209 ¦ Trigg Lake Pump Station | 2025-06-18 | 2025-10-22 |  |  |  | 127
UTL-209 ¦ Trigg Lake Pump Station | 2025-10-23 | 2026-02-19 |  |  |  |  | 120
UTL-209 ¦ Trigg Lake Pump Station | 2026-02-20 | 2026-08-18 | [5 empty] | 180
UTL-211 ¦ Terminal D Grease Trap Rehab | 2023-07-12 | 2023-09-05 |  | 56
UTL-211 ¦ Terminal D Grease Trap Rehab | 2023-09-06 | 2024-07-23 |  |  | 322
UTL-211 ¦ Terminal D Grease Trap Rehab | 2024-07-24 | 2024-11-27 |  |  |  | 127
UTL-211 ¦ Terminal D Grease Trap Rehab | 2024-11-28 | 2025-11-28 |  |  |  |  | 366
UTL-211 ¦ Terminal D Grease Trap Rehab | 2025-11-29 | 2026-05-27 | [5 empty] | 180
UTL-224 ¦ AHQ BAS Rehabilitation | 2024-03-16 | 2024-05-17 |  | 63
UTL-224 ¦ AHQ BAS Rehabilitation | 2024-05-18 | 2025-03-02 |  |  | 289
UTL-224 ¦ AHQ BAS Rehabilitation | 2025-03-03 | 2025-07-09 |  |  |  | 129
UTL-224 ¦ AHQ BAS Rehabilitation | 2025-07-10 | 2026-03-17 |  |  |  |  | 251
UTL-224 ¦ AHQ BAS Rehabilitation | 2026-03-18 | 2026-10-13 | [5 empty] | 210
AFD-040 ¦ Snow & Ice Vehicle Storage Facility | 2020-02-28 | 2024-04-03 |  |  |  | 1497
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2023-01-25 | 2025-03-12 |  |  |  |  | 778
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2023-02-25 | 2023-12-14 |  |  |  |  | 293
NAFD-151 ¦ NE Vault Airfield Lighting Vault HVAC Rehab | 2023-01-18 | 2023-07-20 | 184
NRDS-221 ¦ Hyatt Regency Hotel Garage Driveway Rehabilitation | 2023-02-14 | 2023-07-20 | 157
OTH-068 ¦ Smart Flower Solar Installation | 2018-12-06 | 2026-04-06 |  | 2679
OTH-076 ¦ East Material Management Site | 2020-01-19 | 2024-03-27 |  |  |  | 1530
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2022-12-06 | 2023-11-22 |  |  |  |  | 352
OTH-081 ¦ Materials Testing Lab | 2023-05-09 | 2023-07-17 |  | 70
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2022-02-13 | 2024-02-18 |  |  |  | 736
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2023-05-01 | 2023-10-26 |  |  |  |  | 178
OTH-091 ¦ DCC Elevated Walkways Replacement | 2023-05-08 | 2024-02-02 |  |  | 271
OTH-092 ¦ Rental Car Center (RCC) Bus Wash Building | 2022-10-04 | 2023-07-23 | 293
PAR-043 ¦ Rehabilitation and Improvements for Express North and Employee Lot 1W | 2023-01-10 | 2024-07-05 | 543
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2022-04-20 | 2024-02-09 |  |  | 661
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2023-02-17 | 2023-10-31 | [5 empty] | 256
RDS-186 ¦ Soil Slopes Remediation | 2023-05-09 | 2023-10-05 | [5 empty] | 150
RDS-186-C ¦ Soil Slope Remediation Phase 3 | 2023-03-28 | 2024-04-02 | 372
RDS-217 ¦ Rental Car Center Bus Roads and Bridge Rehabilitation | 2022-09-16 | 2023-06-19 | 277
RDS-222 ¦ Replacement of Retaining Wall 3NW18 | 2023-03-09 | 2024-04-29 | 418
SAF-007 ¦ AOA Gate Replacement | 2023-06-04 | 2023-11-30 | [5 empty] | 180
SAF-092 ¦ Criminal Investigations Shell Space Buildout | 2022-05-09 | 2023-06-19 | 407
SAF-094 ¦ Skylink MSF & 8 Stairwells Fence Replacement | 2022-08-26 | 2023-07-12 | 321
TER-082 ¦ Terminal D Expansion | 2021-08-14 | 2023-11-29 | [5 empty] | 838
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2022-03-04 | 2025-08-21 |  |  |  |  | 1267
TER-180-A ¦ CTX Replacement Project - Terminal D | 2022-09-30 | 2026-03-13 |  |  |  |  | 1261
TER-196 ¦ Grand Hyatt Roof and Joint Sealant | 2021-11-02 | 2024-03-18 | [5 empty] | 868
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2021-06-11 | 2023-06-25 |  | 745
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2022-12-09 | 2023-06-28 |  |  | 202
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2023-03-20 | 2023-10-26 | 221
TER-236-D ¦ Holistic Airside Restroom Program (HARP) Group 3 | 2023-05-05 | 2024-08-25 |  |  | 479
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2023-04-30 | 2023-11-30 |  |  |  | 215
TER-253 ¦ Terminal Dynamic Glass | 2019-05-29 | 2023-10-02 | 1588
TER-256 ¦ Rental Car Center Garage Reallocation | 2019-09-23 | 2024-06-06 |  |  | 1719
TER-271 ¦ Terminal D Roofing Project Phase I | 2019-08-19 | 2026-04-11 |  |  | 2428
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2023-05-18 | 2023-09-14 | [5 empty] | 120
TER-287 ¦ Skybridge A-B Conveyances | 2022-05-15 | 2024-06-08 |  |  |  | 756
TER-308 ¦ Skylink Platform Displays Replacement | 2023-03-08 | 2023-10-12 | 219
TER-309 ¦ Terminal D – CBP Corridors and Vestibules Carpet Replacement | 2023-05-22 | 2024-03-08 | 292
TF2-002 ¦ Supplementary CUP (eCUP) | 2023-05-30 | 2025-02-27 |  |  |  |  | 640
TF2-006 ¦ Airspace Congestion Management and Mitigation | 2019-01-01 | 2027-12-31 | 3287
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2022-06-01 | 2023-08-30 | [5 empty] | 456
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2022-06-01 | 2023-08-30 | [5 empty] | 456
TF2-018-B ¦ Terminal C Renovations | 2020-09-01 | 2023-06-06 |  |  | 1009
TF2-018-B ¦ Confidential Central Option (Planning) | 2021-01-25 | 2025-12-31 | 1802
TF2-018-B ¦ Confidential Central Option (DCC) | 2021-01-25 | 2023-06-06 | 863
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2022-10-03 | 2025-03-21 |  |  |  |  | 901
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2022-11-04 | 2024-08-10 |  |  |  |  | 646
TFD-003 ¦ CTA Expansion - C Pier | 2021-12-17 | 2023-12-05 |  |  | 719
TFD-004 ¦ CTA Expansion - A Pier | 2021-12-17 | 2023-08-31 |  |  | 623
TFD-005 ¦ Terminal C Renovation Phase 1 | 2023-01-10 | 2023-07-05 |  | 176
TFD-005 ¦ Terminal C Renovation Phase 1 | 2023-01-31 | 2024-01-31 |  |  | 365
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2021-09-24 | 2024-04-23 |  |  | 943
TFD-007 ¦ CTA Exp-Term C Garage South | 2021-08-25 | 2023-11-05 |  |  | 802
TFD-008 ¦ CTA Exp-Utility Corr | 2023-01-10 | 2023-07-09 |  |  |  | 181
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2021-07-02 | 2024-03-31 |  | 1004
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2021-12-17 | 2023-11-30 |  |  | 714
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2022-10-28 | 2023-12-22 |  |  |  |  | 421
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2023-05-18 | 2023-12-01 |  |  |  | 198
TFF-003 ¦ Terminal F Civil & Utility | 2023-05-27 | 2023-06-25 |  | 30
TFF-003 ¦ Terminal F Civil & Utility | 2023-06-16 | 2024-01-04 |  |  | 203
TFF-004 ¦ BHS, Goods Delivery & Services* | 2023-05-18 | 2023-06-30 |  | 44
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2023-01-08 | 2024-01-21 |  |  | 378
TRIP-09 ¦ TRIP - Terminal A Pet Conveyor | 2017-11-03 | 2030-10-21 |  |  | 4736
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2023-05-31 | 2023-10-17 | [5 empty] | 139
UTL-045 ¦ East & West Potable Water Pump Stations | 2023-02-26 | 2023-10-08 |  |  |  | 225
UTL-079 ¦ Energy Plaza - Replace 480V Switchgear & Protective Relays | 2022-05-06 | 2024-02-21 | 657
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2023-01-12 | 2023-09-26 |  |  | 258
UTL-205-A ¦ Skylink Obsolescence - Phase1 | 2022-02-07 | 2023-09-13 | 584
UTL-211 ¦ Terminal D Grease Trap Rehab | 2022-11-17 | 2023-07-07 | 233
UTL-223 ¦ South Sludge Lagoon Rehabilitation | 2023-05-09 | 2024-03-08 | 305
UTL-224 ¦ AHQ BAS Rehabilitation | 2023-05-22 | 2024-03-08 | 292
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2022-06-06 | 2023-06-06 |  |  |  | 364
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2021-09-24 | 2023-06-06 |  |  |  | 620
UTL-017 ¦ Rehabilitate Open Channels | 2023-03-04 | 2023-06-06 | [5 empty] | 94
AFD-048-A ¦ Southwest End-Around Taxiway Project | 2018-09-01 | 2019-01-03 |  | 124
AFD-062-A ¦ RWY 17C/35C Reconstruction -Taxiway Mike North (Const. Pkg. - III) | 2016-09-01 | 2016-11-05 |  | 65
AFD-062-B ¦ RWY 17C/35C Reconstruction -Taxiway Mike South (Const. Pkg. - II) | 2016-09-01 | 2016-11-06 |  | 66
AFD-102 ¦ Taxiway F Rehabilitation | 2014-04-28 | 2015-02-28 |  | 306
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2018-05-13 | 2018-05-13 | 0
RDS-001 ¦ Skylink ATC Replacement | 2018-08-16 | 2018-12-07 | 113
RDS-001 ¦ Skylink ATC Replacement | 2018-12-08 | 2019-06-27 |  | 201
RDS-008 ¦ Repair of Southbound Ramp to Crossover #4 Retaining Wall | 2017-04-19 | 2017-09-22 |  | 156
SAF-007 ¦ AOA Gate Replacement | 2018-03-07 | 2018-07-20 |  | 135
TER-072 ¦ Upgrade Passenger Boarding Bridge (PBBs) Equipment - Terminal E | 2018-07-06 | 2018-08-01 |  | 26
TER-072 ¦ Upgrade Passenger Boarding Bridge (PBBs) Equipment - Terminal E | 2018-08-01 | 2019-02-10 |  |  | 193
TER-082 ¦ Terminal D Expansion | 2018-03-20 | 2018-03-20 | 0
TER-082 ¦ Terminal D Expansion | 2018-04-16 | 2018-07-15 |  |  | 90
TER-176 ¦ Terminal D UPS Replacement | 2018-07-03 | 2018-09-27 |  | 86
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2018-12-14 | 2018-12-14 | 0
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2018-12-14 | 2018-12-15 |  | 1
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2018-12-14 | 2018-12-15 |  |  | 1
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2018-12-14 | 2018-12-15 |  |  |  | 1
TER-255 ¦ Terminal B Mainline Expansion | 2018-11-01 | 2018-11-30 | 29
TER-255 ¦ Terminal B Mainline Expansion | 2018-12-01 | 2018-12-10 |  | 9
TER-255 ¦ Terminal B Mainline Expansion | 2018-12-11 | 2018-12-16 |  |  | 5
TER-255 ¦ Terminal B Mainline Expansion | 2018-12-17 | 2018-12-18 |  |  |  | 1
TRIP-12 ¦ TRIP - Parking Lot Removal | 2018-05-16 | 2018-07-13 |  | 58
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2019-01-09 | 2019-01-09 | 0
UTL-045 ¦ East & West Potable Water Pump Stations | 2016-08-29 | 2017-05-23 |  | 267
AFD-040 ¦ Snow & Ice Vehicle Storage Facility | 2016-06-13 | 2019-06-20 |  | 1102
AFD-040 ¦ Snow & Ice Vehicle Storage Facility | 2019-06-21 | 2020-02-28 |  |  | 252
AFD-048-A ¦ Southwest End-Around Taxiway Project | 2019-01-04 | 2022-07-14 |  |  | 1287
AFD-048-A ¦ Southwest End-Around Taxiway Project | 2022-06-12 | 2023-01-02 |  |  |  | 205
AFD-050-B ¦ NE End-Around Taxiway Package II - Taxiway Papa Realignment | 2017-05-23 | 2017-07-12 |  | 51
AFD-050-B ¦ NE End-Around Taxiway Package II - Taxiway Papa Realignment | 2017-07-13 | 2020-04-23 |  |  | 1015
AFD-050-B ¦ NE End-Around Taxiway Package II - Taxiway Papa Realignment | 2020-04-22 | 2020-09-07 |  |  |  | 139
AFD-050-B ¦ NE End-Around Taxiway Package II - Taxiway Papa Realignment | 2020-09-14 | 2022-03-30 |  |  |  |  | 563
AFD-050-C ¦ NE End-Around Taxiway Package III - Glycol Facilities Relocation | 2017-05-23 | 2017-07-12 |  | 51
AFD-050-C ¦ NE End-Around Taxiway Package III - Glycol Facilities Relocation | 2017-07-13 | 2019-03-04 |  |  | 599
AFD-050-C ¦ NE End-Around Taxiway Package III - Glycol Facilities Relocation | 2019-03-10 | 2019-07-08 |  |  |  | 120
AFD-050-C ¦ NE End-Around Taxiway Package III - Glycol Facilities Relocation | 2019-07-09 | 2020-09-30 |  |  |  |  | 449
AFD-062-B ¦ RWY 17C/35C Reconstruction -Taxiway Mike South (Const. Pkg. - II) | 2016-11-07 | 2019-05-14 |  |  | 917
AFD-062-B ¦ RWY 17C/35C Reconstruction -Taxiway Mike South (Const. Pkg. - II) | 2019-05-20 | 2019-09-24 |  |  |  | 127
AFD-062-B ¦ RWY 17C/35C Reconstruction -Taxiway Mike South (Const. Pkg. - II) | 2019-09-30 | 2021-05-14 |  |  |  |  | 593
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2020-08-10 | 2020-10-15 | 66
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2020-10-15 | 2020-12-16 |  | 62
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2020-12-16 | 2022-09-02 |  |  | 626
AFD-065 ¦ Runway 17R/35L Rehabilitation | 2022-09-18 | 2023-01-09 |  |  |  | 114
AFD-102 ¦ Taxiway F Rehabilitation | 2015-03-02 | 2019-03-08 |  |  | 1468
AFD-102 ¦ Taxiway F Rehabilitation | 2019-03-09 | 2019-09-28 |  |  |  | 203
AFD-102 ¦ Taxiway F Rehabilitation | 2019-10-07 | 2022-03-01 |  |  |  |  | 876
AFD-124 ¦ Taxiway G Emergency Repair | 2018-09-17 | 2019-01-30 | 135
AFD-124 ¦ Taxiway G Emergency Repair | 2019-02-25 | 2019-02-25 |  | 0
AFD-124 ¦ Taxiway G Emergency Repair | 2019-02-25 | 2019-03-08 |  |  | 12
AFD-124 ¦ Taxiway G Emergency Repair | 2019-03-09 | 2019-09-27 |  |  |  | 203
AFD-124 ¦ Taxiway G Emergency Repair | 2019-10-07 | 2021-06-10 |  |  |  |  | 612
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2020-01-15 | 2020-07-06 | 173
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2020-08-10 | 2020-12-08 |  | 120
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2020-12-07 | 2021-05-10 |  |  | 154
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2021-05-16 | 2022-05-27 |  |  |  | 377
AFD-141 ¦ Airfield Pavement Remediation | 2021-03-04 | 2021-06-09 | 97
AFD-141 ¦ Airfield Pavement Remediation | 2021-07-20 | 2021-09-29 |  | 72
AFD-141 ¦ Airfield Pavement Remediation | 2021-09-30 | 2022-03-25 |  |  | 176
AFD-141 ¦ Airfield Pavement Remediation | 2022-03-27 | 2022-06-23 |  |  |  | 89
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2022-12-25 | 2022-12-28 | 3
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2022-12-28 | 2023-01-08 |  | 11
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2023-01-09 | 2023-02-14 |  |  | 36
AFD-141-A ¦ Airfield Pavement Remediation 2023 | 2023-02-15 | 2023-02-25 |  |  |  | 11
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2021-04-23 | 2021-11-05 | 197
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2021-11-06 | 2022-01-24 |  | 80
NOTH-020 ¦ RAC Elevator Modular Modernization | 2021-04-02 | 2021-08-23 | 144
NOTH-020 ¦ RAC Elevator Modular Modernization | 2022-03-22 | 2022-05-24 |  | 64
NOTH-020 ¦ RAC Elevator Modular Modernization | 2022-05-24 | 2023-02-17 |  |  | 270
NOTH-067 ¦ RCC Restroom Renovations | 2017-04-26 | 2017-05-18 |  | 22
NOTH-067 ¦ RCC Restroom Renovations | 2017-05-18 | 2017-09-12 |  |  | 118
NOTH-067 ¦ RCC Restroom Renovations | 2017-10-22 | 2019-05-06 |  |  |  | 561
NOTH-067 ¦ RCC Restroom Renovations | 2019-05-02 | 2022-09-16 |  |  |  |  | 1233
NOTH-075 ¦ Rental Car Center - Restroom Renovations Phase II | 2019-08-19 | 2019-10-21 |  | 64
NOTH-075 ¦ Rental Car Center - Restroom Renovations Phase II | 2019-10-21 | 2021-07-27 |  |  | 645
NOTH-075 ¦ Rental Car Center - Restroom Renovations Phase II | 2021-07-28 | 2022-11-03 |  |  |  | 464
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2022-03-10 | 2023-03-08 | 364
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2020-04-03 | 2021-04-29 | 391
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2021-03-01 | 2022-02-16 |  | 352
NSAF-076 ¦ ARFF Station Consolidation – East & West Locations | 2022-02-17 | 2022-06-06 |  |  | 110
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2021-05-31 | 2021-05-31 | 0
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2021-06-01 | 2021-06-30 |  | 29
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2021-07-01 | 2021-07-31 |  |  | 30
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2021-08-01 | 2021-12-28 |  |  |  | 150
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2022-01-19 | 2022-08-05 |  |  |  |  | 199
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2021-11-11 | 2023-04-06 | 512
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2023-04-25 | 2023-06-04 |  | 40
NTER-302 ¦ Terminal Exit Lane Installation | 2022-02-07 | 2022-07-08 | 152
NTER-302 ¦ Terminal Exit Lane Installation | 2022-07-08 | 2022-09-02 |  | 57
NTER-302 ¦ Terminal Exit Lane Installation | 2022-09-02 | 2022-12-13 |  |  | 101
NTER-302 ¦ Terminal Exit Lane Installation | 2023-01-10 | 2023-02-17 |  |  |  | 38
NTER-302 ¦ Terminal Exit Lane Installation | 2023-02-15 | 2023-05-01 |  |  |  |  | 76
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2021-04-21 | 2021-10-04 | 166
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2022-02-14 | 2022-04-25 |  | 71
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2022-04-25 | 2022-11-19 |  |  | 209
NUTL-010 ¦ RAC Garage Dry Sprinkler System | 2022-11-20 | 2023-06-02 |  |  |  | 195
OTH-026-C ¦ DFW Facilities Relocation and Consolidation - Phase 1 Roads and Utilities | 2018-05-14 | 2018-07-13 |  | 61
OTH-026-C ¦ DFW Facilities Relocation and Consolidation - Phase 1 Roads and Utilities | 2018-07-16 | 2019-01-04 |  |  | 172
OTH-026-C ¦ DFW Facilities Relocation and Consolidation - Phase 1 Roads and Utilities | 2019-01-06 | 2019-07-15 |  |  |  | 190
OTH-026-C ¦ DFW Facilities Relocation and Consolidation - Phase 1 Roads and Utilities | 2019-07-22 | 2021-10-15 |  |  |  |  | 817
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2018-05-14 | 2018-07-15 |  | 62
OTH-026-D ¦ Spent Aircraft Deicing Fluid Pipeline Realignment at Southwest Campus | 2018-07-16 | 2019-01-04 |  |  | 172
OTH-068 ¦ Smart Flower Solar Installation | 2018-04-23 | 2018-12-19 | 240
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2018-12-27 | 2022-03-03 | 1163
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2022-03-03 | 2022-10-13 |  | 224
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2023-01-12 | 2023-02-17 |  |  | 37
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2019-06-04 | 2020-10-14 | 499
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2020-10-16 | 2021-01-13 |  | 90
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2021-01-13 | 2022-01-31 |  |  | 383
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2022-02-20 | 2022-07-11 |  |  |  | 142
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2019-05-24 | 2019-12-11 | 201
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2019-12-12 | 2020-04-16 |  | 127
OTH-074 ¦ Replace HVAC Systems at PMM Building Project | 2020-05-08 | 2020-10-20 |  |  | 166
OTH-076 ¦ East Material Management Site | 2019-10-04 | 2019-12-13 | 71
OTH-076 ¦ East Material Management Site | 2019-10-30 | 2020-01-16 |  | 79
OTH-076 ¦ East Material Management Site | 2019-11-23 | 2020-01-16 |  |  | 55
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2019-10-07 | 2020-04-20 | 196
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2020-05-25 | 2021-01-11 |  | 231
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2021-01-13 | 2022-05-07 |  |  | 480
OTH-077 ¦ SkyLink MSF Test Track Remediation | 2022-06-19 | 2022-12-06 |  |  |  | 171
OTH-078 ¦ Skylink UPSs Replacement | 2020-02-11 | 2020-07-13 | 153
OTH-078 ¦ Skylink UPSs Replacement | 2020-09-08 | 2020-11-17 |  | 70
OTH-078 ¦ Skylink UPSs Replacement | 2020-11-17 | 2021-08-31 |  |  | 288
OTH-078 ¦ Skylink UPSs Replacement | 2021-09-12 | 2022-02-14 |  |  |  | 156
OTH-078 ¦ Skylink UPSs Replacement | 2022-02-15 | 2022-11-14 |  |  |  |  | 273
OTH-081 ¦ Materials Testing Lab | 2020-02-18 | 2023-04-14 | 1152
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2020-05-28 | 2021-04-06 | 313
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2021-04-14 | 2021-06-11 |  | 58
OTH-082 ¦ Integrated Operations Center (IOC) Backup Facility | 2021-06-14 | 2022-01-31 |  |  | 232
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2020-12-15 | 2021-03-09 | 85
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2021-03-12 | 2021-04-06 |  | 26
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2021-04-06 | 2021-09-20 |  |  | 167
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2021-09-20 | 2022-02-10 |  |  |  | 144
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2022-02-28 | 2022-10-28 |  |  |  |  | 243
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2021-12-20 | 2022-04-26 | 128
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2022-04-26 | 2022-07-01 |  | 67
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2022-07-01 | 2022-09-09 |  |  | 70
OTH-085 ¦ International Parkway Signage Program Digital Signs | 2022-10-01 | 2023-05-01 |  |  |  | 212
OTH-086 ¦ Old Conveyances Replacement | 2021-12-29 | 2022-10-12 | 288
OTH-091 ¦ DCC Elevated Walkways Replacement | 2022-08-29 | 2023-03-30 | 213
OTH-091 ¦ DCC Elevated Walkways Replacement | 2023-03-30 | 2023-05-08 |  | 40
OTH-093 ¦ Parking Customer Service Room Expansion | 2022-11-02 | 2023-03-29 | 148
OTH-093 ¦ Parking Customer Service Room Expansion | 2023-04-04 | 2023-05-29 |  | 56
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2018-08-10 | 2020-09-16 | 768
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2020-10-26 | 2021-03-14 |  | 139
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2021-03-14 | 2021-11-19 |  |  | 251
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2021-11-21 | 2022-07-11 |  |  |  | 233
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2022-07-12 | 2023-05-16 |  |  |  |  | 309
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2021-10-07 | 2022-01-06 | 92
PAR-073 ¦ Rehabilitation and Improvement of Employee Southeast Lot | 2022-02-28 | 2022-04-20 |  | 52
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2019-02-20 | 2019-09-24 | 217
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2019-09-25 | 2019-10-22 |  | 28
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2019-10-23 | 2021-03-01 |  |  | 495
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2021-04-27 | 2021-08-02 |  |  |  | 97
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2021-08-09 | 2022-01-06 |  |  |  |  | 151
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2022-03-02 | 2022-03-03 | 1
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2022-05-02 | 2022-06-29 |  | 58
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2022-07-11 | 2022-09-02 |  |  | 54
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2022-09-01 | 2022-12-01 |  |  |  | 90
PSR-050 ¦ D-S Ramp Sink & D5 Tile | 2023-01-02 | 2023-01-27 |  |  |  |  | 26
RDS-001 ¦ Skylink ATC Replacement | 2019-06-28 | 2020-09-30 |  |  | 460
RDS-001 ¦ Skylink ATC Replacement | 2020-09-30 | 2020-09-30 |  |  |  | 0
RDS-007 ¦ East West Connector Roadway | 2018-09-18 | 2020-08-05 |  | 687
RDS-007 ¦ East West Connector Roadway | 2020-08-06 | 2023-01-31 |  |  | 909
RDS-008 ¦ Repair of Southbound Ramp to Crossover #4 Retaining Wall | 2017-09-22 | 2018-05-04 |  |  | 225
RDS-008 ¦ Repair of Southbound Ramp to Crossover #4 Retaining Wall | 2019-06-20 | 2020-01-16 |  |  |  | 211
RDS-008 ¦ Repair of Southbound Ramp to Crossover #4 Retaining Wall | 2020-01-17 | 2022-10-27 |  |  |  |  | 1014
RDS-015 ¦ Rehabilitate Landside Roadways & Bridges Phase 4A | 2016-07-14 | 2018-03-07 |  | 602
RDS-015 ¦ Rehabilitate Landside Roadways & Bridges Phase 4A | 2018-03-08 | 2020-11-13 |  |  | 981
RDS-015 ¦ Rehabilitate Landside Roadways & Bridges Phase 4A | 2021-01-24 | 2021-07-20 |  |  |  | 177
RDS-015 ¦ Rehabilitate Landside Roadways & Bridges Phase 4A | 2021-07-20 | 2022-10-27 |  |  |  |  | 465
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2015-11-11 | 2016-07-14 | 247
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2018-06-25 | 2018-11-07 |  | 135
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2018-06-25 | 2019-06-19 |  |  | 359
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2019-08-07 | 2020-01-16 |  |  |  | 163
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2020-01-17 | 2022-10-27 |  |  |  |  | 1014
RDS-025 ¦ Cloverleafs & Ramps North Airfield Drive Bridge | 2017-05-16 | 2019-04-29 |  | 713
RDS-025 ¦ Cloverleafs & Ramps North Airfield Drive Bridge | 2019-05-01 | 2022-02-21 |  |  | 1028
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2017-11-28 | 2018-10-29 | 335
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2018-12-17 | 2019-04-08 |  | 112
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2019-04-08 | 2020-05-22 |  |  | 411
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2020-06-09 | 2020-09-16 |  |  |  | 100
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2020-09-17 | 2021-06-02 |  |  |  |  | 259
RDS-029-B ¦ Glade Road and Bridge Replacement | 2017-11-16 | 2018-10-17 | 335
RDS-029-B ¦ Glade Road and Bridge Replacement | 2019-01-23 | 2019-02-12 |  | 20
RDS-029-B ¦ Glade Road and Bridge Replacement | 2019-02-27 | 2021-11-04 |  |  | 982
RDS-029-B ¦ Glade Road and Bridge Replacement | 2021-10-04 | 2021-11-04 |  |  |  | 31
RDS-045 ¦ Terminal D Upper Level Roadway & Sidewalks Expansion Joint Replacement | 2017-05-30 | 2018-01-05 |  | 220
RDS-045 ¦ Terminal D Upper Level Roadway & Sidewalks Expansion Joint Replacement | 2018-01-11 | 2019-12-20 |  |  | 708
RDS-045 ¦ Terminal D Upper Level Roadway & Sidewalks Expansion Joint Replacement | 2019-12-22 | 2020-06-17 |  |  |  | 178
RDS-045 ¦ Terminal D Upper Level Roadway & Sidewalks Expansion Joint Replacement | 2020-06-18 | 2021-06-18 |  |  |  |  | 365
RDS-050-A ¦ Skylink Structural Improvements | 2017-04-21 | 2017-05-10 | 19
RDS-050-A ¦ Skylink Structural Improvements | 2017-05-11 | 2017-07-29 |  | 79
RDS-050-A ¦ Skylink Structural Improvements | 2017-07-29 | 2018-03-02 |  |  | 215
RDS-050-A ¦ Skylink Structural Improvements | 2018-03-05 | 2018-06-20 |  |  |  | 108
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2021-07-02 | 2022-02-18 | 232
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2022-03-14 | 2022-06-07 |  | 86
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2022-06-08 | 2022-12-09 |  |  | 185
RDS-056 ¦ Carousel/Secondary Roadway Signage Program | 2023-01-01 | 2023-05-31 |  |  |  | 151
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2018-11-20 | 2019-02-12 | 84
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2019-02-13 | 2021-04-11 |  | 788
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2021-04-12 | 2022-10-28 |  |  | 565
RDS-186 ¦ Soil Slopes Remediation | 2019-10-11 | 2020-03-05 | 146
RDS-186 ¦ Soil Slopes Remediation | 2020-09-07 | 2021-02-03 |  | 149
RDS-186 ¦ Soil Slopes Remediation | 2021-02-03 | 2021-10-25 |  |  | 264
RDS-186 ¦ Soil Slopes Remediation | 2021-11-08 | 2022-04-15 |  |  |  | 159
RDS-186 ¦ Soil Slopes Remediation | 2022-04-15 | 2023-05-08 |  |  |  |  | 388
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2020-11-03 | 2020-11-23 | 21
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2020-11-23 | 2021-02-03 |  | 72
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2021-02-03 | 2022-01-25 |  |  | 356
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2022-01-26 | 2022-04-15 |  |  |  | 79
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2022-01-21 | 2022-03-31 | 69
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2022-04-01 | 2022-04-30 |  | 29
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2022-05-01 | 2022-06-30 |  |  | 60
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2022-07-01 | 2022-07-25 |  |  |  | 24
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2022-07-25 | 2022-12-05 |  |  |  |  | 134
SAF-007 ¦ AOA Gate Replacement | 2018-07-20 | 2019-08-31 |  |  | 407
SAF-007 ¦ AOA Gate Replacement | 2019-09-01 | 2020-01-27 |  |  |  | 149
SAF-007 ¦ AOA Gate Replacement | 2020-01-27 | 2023-06-03 |  |  |  |  | 1224
SAF-012 ¦ DPS Police Outdoor Range Upgrade | 2017-12-12 | 2019-12-19 |  | 737
SAF-012 ¦ DPS Police Outdoor Range Upgrade | 2019-12-20 | 2021-06-18 |  |  | 546
SAF-012 ¦ DPS Police Outdoor Range Upgrade | 2021-06-19 | 2023-03-04 |  |  |  | 624
SAF-028 ¦ Integrated AOC-EOC Center | 2017-07-24 | 2017-08-30 |  | 38
SAF-028 ¦ Integrated AOC-EOC Center | 2017-08-30 | 2019-08-15 |  |  | 715
SAF-028 ¦ Integrated AOC-EOC Center | 2019-08-15 | 2019-08-15 |  |  |  | 0
SAF-028 ¦ Integrated AOC-EOC Center | 2019-08-16 | 2021-01-06 |  |  |  |  | 509
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2020-10-12 | 2022-06-27 | 624
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2022-06-28 | 2022-10-27 |  | 122
SAF-066 ¦ Curbside Barrier Installation | 2019-10-02 | 2020-07-13 | 285
SAF-066 ¦ Curbside Barrier Installation | 2020-08-05 | 2020-10-27 |  | 84
SAF-066 ¦ Curbside Barrier Installation | 2020-10-27 | 2021-04-30 |  |  | 186
SAF-066 ¦ Curbside Barrier Installation | 2021-05-02 | 2021-08-30 |  |  |  | 121
SAF-066 ¦ Curbside Barrier Installation | 2021-09-15 | 2022-08-31 |  |  |  |  | 351
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2019-08-20 | 2020-04-17 | 241
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2020-04-21 | 2020-06-09 |  | 49
SAF-072 ¦ DPS Consolidated K9 & Hazardous Devices Unit Facility | 2020-06-09 | 2021-05-17 |  |  | 342
SAF-078 ¦ Employee Inspection Portal Redesign | 2019-02-28 | 2019-06-20 | 113
SAF-078 ¦ Employee Inspection Portal Redesign | 2019-05-28 | 2020-01-28 |  | 246
SAF-078 ¦ Employee Inspection Portal Redesign | 2020-01-29 | 2022-09-29 |  |  | 974
SAF-078 ¦ Employee Inspection Portal Redesign | 2022-09-29 | 2022-09-29 |  |  |  | 0
TECH-102 ¦ Replacement AACS (RAACS) Program | 2020-06-30 | 2021-04-05 | 279
TECH-102 ¦ Replacement AACS (RAACS) Program | 2022-01-17 | 2023-05-24 |  | 493
TER-007 ¦ Terminal B & E Replace Passenger Boarding Bridges (PBBs) B9B, B10B, E31, & E34 | 2018-01-19 | 2018-03-23 |  | 64
TER-007 ¦ Terminal B & E Replace Passenger Boarding Bridges (PBBs) B9B, B10B, E31, & E34 | 2018-03-26 | 2018-11-30 |  |  | 249
TER-007 ¦ Terminal B & E Replace Passenger Boarding Bridges (PBBs) B9B, B10B, E31, & E34 | 2018-12-02 | 2019-06-04 |  |  |  | 184
TER-007 ¦ Terminal B & E Replace Passenger Boarding Bridges (PBBs) B9B, B10B, E31, & E34 | 2019-06-07 | 2021-09-15 |  |  |  |  | 832
TER-021-A ¦ Term-D Systems Rehabilitation | 2018-08-08 | 2019-06-19 |  | 315
TER-021-A ¦ Term-D Systems Rehabilitation | 2019-06-20 | 2019-12-10 |  |  | 174
TER-021-A ¦ Term-D Systems Rehabilitation | 2020-04-03 | 2020-10-27 |  |  |  | 207
TER-021-A ¦ Term-D Systems Rehabilitation | 2020-11-16 | 2022-06-20 |  |  |  |  | 582
TER-067 ¦ Term-A Roofing Project | 2018-07-06 | 2018-09-30 | 86
TER-067 ¦ Term-A Roofing Project | 2018-10-01 | 2018-10-18 |  | 17
TER-067 ¦ Term-A Roofing Project | 2018-10-19 | 2019-07-31 |  |  | 285
TER-067 ¦ Term-A Roofing Project | 2019-08-06 | 2021-11-04 |  |  |  | 821
TER-072 ¦ Upgrade Passenger Boarding Bridge (PBBs) Equipment - Terminal E | 2019-02-10 | 2019-07-21 |  |  |  | 162
TER-072 ¦ Upgrade Passenger Boarding Bridge (PBBs) Equipment - Terminal E | 2019-07-22 | 2021-11-24 |  |  |  |  | 857
TER-082 ¦ Terminal D Expansion | 2018-03-21 | 2018-04-11 |  | 22
TER-082 ¦ Terminal D Expansion | 2018-07-16 | 2019-05-30 |  |  |  | 318
TER-082 ¦ Terminal D Expansion | 2019-05-31 | 2021-08-13 |  |  |  |  | 805
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2018-02-02 | 2018-12-21 | 322
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2018-12-21 | 2019-03-04 |  | 73
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2019-03-04 | 2019-06-28 |  |  | 117
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2019-07-02 | 2019-08-09 |  |  |  | 38
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2019-08-09 | 2019-10-09 |  |  |  |  | 61
TER-160 ¦ Terminal D Board Owned PBB Rehab | 2018-01-30 | 2018-05-11 |  | 102
TER-160 ¦ Terminal D Board Owned PBB Rehab | 2018-05-14 | 2019-06-04 |  |  | 386
TER-160 ¦ Terminal D Board Owned PBB Rehab | 2019-06-09 | 2019-10-15 |  |  |  | 129
TER-160 ¦ Terminal D Board Owned PBB Rehab | 2019-10-16 | 2020-07-02 |  |  |  |  | 261
TER-176 ¦ Terminal D UPS Replacement | 2018-09-28 | 2019-02-15 |  |  | 141
TER-176 ¦ Terminal D UPS Replacement | 2019-03-13 | 2019-09-30 |  |  |  | 201
TER-176 ¦ Terminal D UPS Replacement | 2019-09-30 | 2020-10-19 |  |  |  |  | 386
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2018-09-18 | 2019-04-28 | 222
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2019-04-29 | 2019-06-26 |  | 59
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2019-06-27 | 2021-05-03 |  |  | 677
TER-180 ¦ CTX Replacement Project - Terminals A,B,C | 2021-05-03 | 2022-03-04 |  |  |  | 306
TER-180-A ¦ CTX Replacement Project - Terminal D | 2018-09-18 | 2019-04-28 | 223
TER-180-A ¦ CTX Replacement Project - Terminal D | 2019-04-29 | 2019-06-26 |  | 59
TER-180-A ¦ CTX Replacement Project - Terminal D | 2019-06-27 | 2022-04-04 |  |  | 1013
TER-180-A ¦ CTX Replacement Project - Terminal D | 2022-04-17 | 2022-09-29 |  |  |  | 166
TER-196 ¦ Grand Hyatt Roof and Joint Sealant | 2018-07-23 | 2018-10-22 |  | 92
TER-196 ¦ Grand Hyatt Roof and Joint Sealant | 2018-10-22 | 2019-12-30 |  |  | 434
TER-196 ¦ Grand Hyatt Roof and Joint Sealant | 2019-12-31 | 2020-06-30 |  |  |  | 182
TER-196 ¦ Grand Hyatt Roof and Joint Sealant | 2020-07-20 | 2021-11-01 |  |  |  |  | 470
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2018-09-04 | 2023-04-13 | 1682
TER-236-B ¦ Holistic Airside Restrooms Program (HARP) - Phase 1 | 2019-01-25 | 2021-06-11 | 869
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2022-01-31 | 2022-07-20 | 170
TER-236-C ¦ Holistic Airside Restroom Program (HARP) Group 2 | 2022-07-20 | 2022-12-08 |  | 141
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2019-07-08 | 2021-11-10 | 857
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2021-11-23 | 2022-05-25 |  | 183
TER-247 ¦ Terminal Cabinet and Carpet Replacement | 2022-05-25 | 2023-04-24 |  |  | 335
TER-256 ¦ Rental Car Center Garage Reallocation | 2018-11-07 | 2019-05-15 | 190
TER-256 ¦ Rental Car Center Garage Reallocation | 2019-05-17 | 2019-09-20 |  | 127
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2018-08-28 | 2019-09-20 | 388
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2019-07-08 | 2019-11-07 |  | 123
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2019-11-11 | 2020-07-03 |  |  | 235
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2020-07-06 | 2021-02-08 |  |  |  | 217
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2018-06-11 | 2019-03-12 | 274
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2019-04-10 | 2019-09-23 |  | 166
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2019-09-23 | 2020-09-30 |  |  | 373
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2020-10-04 | 2021-03-20 |  |  |  | 168
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2021-03-26 | 2022-09-04 |  |  |  |  | 528
TER-271 ¦ Terminal D Roofing Project Phase I | 2019-03-08 | 2019-04-30 | 53
TER-271 ¦ Terminal D Roofing Project Phase I | 2019-05-01 | 2019-08-18 |  | 109
TER-273 ¦ Sky-link Restrooms Initiative | 2019-04-15 | 2019-05-23 | 38
TER-273 ¦ Sky-link Restrooms Initiative | 2019-05-24 | 2019-07-12 |  | 49
TER-273 ¦ Sky-link Restrooms Initiative | 2019-07-12 | 2019-09-23 |  |  | 73
TER-273 ¦ Sky-link Restrooms Initiative | 2019-09-23 | 2020-05-31 |  |  |  | 251
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2021-02-24 | 2021-06-09 | 105
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2021-07-19 | 2021-11-21 |  | 126
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2021-11-22 | 2022-04-19 |  |  | 149
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2022-05-08 | 2022-09-10 |  |  |  | 126
TER-274 ¦ Passenger Boarding Bridge Program #1 | 2022-09-12 | 2023-05-17 |  |  |  |  | 248
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2022-01-24 | 2022-09-28 | 247
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2022-10-06 | 2022-12-16 |  | 72
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2019-07-30 | 2020-04-22 | 268
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2020-06-01 | 2020-11-13 |  | 166
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2020-11-23 | 2021-05-20 |  |  | 179
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2021-05-30 | 2021-10-18 |  |  |  | 142
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2021-10-18 | 2022-08-24 |  |  |  |  | 311
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2022-01-28 | 2022-06-15 | 139
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2022-06-14 | 2022-09-06 |  | 85
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2022-09-07 | 2023-04-19 |  |  | 225
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2019-08-01 | 2020-03-13 | 226
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2020-03-31 | 2020-10-16 |  | 199
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2020-10-16 | 2021-10-08 |  |  | 358
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2021-10-10 | 2022-04-07 |  |  |  | 180
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2022-04-08 | 2023-02-25 |  |  |  |  | 324
TER-286 ¦ Terminal Electrical Systems Upgrade | 2020-01-21 | 2020-12-07 | 321
TER-286 ¦ Terminal Electrical Systems Upgrade | 2020-12-08 | 2021-02-24 |  | 79
TER-286 ¦ Terminal Electrical Systems Upgrade | 2021-02-25 | 2021-09-14 |  |  | 202
TER-286 ¦ Terminal Electrical Systems Upgrade | 2021-10-03 | 2022-02-11 |  |  |  | 131
TER-286 ¦ Terminal Electrical Systems Upgrade | 2022-02-25 | 2023-01-23 |  |  |  |  | 333
TER-287 ¦ Skybridge A-B Conveyances | 2020-04-14 | 2021-04-13 | 364
TER-287 ¦ Skybridge A-B Conveyances | 2021-04-07 | 2021-07-19 |  | 103
TER-287 ¦ Skybridge A-B Conveyances | 2021-07-20 | 2022-04-19 |  |  | 274
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2021-03-31 | 2021-06-09 | 70
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2021-08-05 | 2022-02-02 |  | 182
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2019-10-04 | 2019-12-13 | 70
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2020-01-17 | 2020-04-13 |  | 87
TER-290 ¦ Terminal D Roofing Project Phase 2 | 2020-04-14 | 2020-12-07 |  |  | 237
TER-297 ¦ Term-D Sewer Lift Station | 2020-08-13 | 2020-12-07 | 116
TER-297 ¦ Term-D Sewer Lift Station | 2020-12-07 | 2021-02-10 |  | 66
TER-297 ¦ Term-D Sewer Lift Station | 2021-02-15 | 2021-10-23 |  |  | 251
TER-297 ¦ Term-D Sewer Lift Station | 2021-10-24 | 2022-04-10 |  |  |  | 169
TER-301 ¦ Skylink Elevator Replacement Project | 2021-12-29 | 2022-06-21 | 175
TER-301 ¦ Skylink Elevator Replacement Project | 2022-08-02 | 2022-11-11 |  | 102
TF2-002 ¦ Supplementary CUP (eCUP) | 2019-08-19 | 2019-08-28 | 10
TF2-002 ¦ Supplementary CUP (eCUP) | 2019-08-29 | 2020-02-14 |  | 170
TF2-002 ¦ Supplementary CUP (eCUP) | 2020-02-14 | 2023-02-04 |  |  | 1087
TF2-002 ¦ Supplementary CUP (eCUP) | 2023-02-04 | 2023-05-30 |  |  |  | 115
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2020-04-16 | 2020-05-18 | 32
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2020-05-24 | 2020-09-08 |  | 107
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2020-09-08 | 2021-02-03 |  |  | 148
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2021-02-03 | 2021-02-03 |  |  |  | 0
TF2-015-A ¦ Terminal C High C Gates Demolition and Rebuild | 2021-02-04 | 2022-05-31 |  |  |  |  | 482
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2020-04-16 | 2020-05-18 | 32
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2020-05-27 | 2020-09-14 |  | 110
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2021-01-08 | 2021-05-03 |  |  | 115
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2021-05-03 | 2021-08-12 |  |  |  | 102
TF2-015-B ¦ Design and Construction of Fit Out and Enabling Projects for High C | 2021-09-16 | 2022-05-31 |  |  |  |  | 258
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2020-11-02 | 2021-06-16 | 226
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2021-05-26 | 2021-08-12 |  | 77
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2021-08-12 | 2022-03-14 |  |  | 215
TFD-001 ¦ East Airfield Lighting Vault Relocations | 2022-03-16 | 2022-10-02 |  |  |  | 201
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2020-11-02 | 2021-06-16 | 226
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2021-05-26 | 2021-08-12 |  | 77
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2021-08-12 | 2022-05-20 |  |  | 281
TFD-002 ¦ CTA Exp-Airfield Ramp Efficiency | 2022-05-21 | 2022-11-03 |  |  |  | 165
TFD-003 ¦ CTA Expansion - C Pier | 2020-11-02 | 2021-06-16 | 226
TFD-003 ¦ CTA Expansion - C Pier | 2021-04-12 | 2021-12-17 |  | 249
TFD-004 ¦ CTA Expansion - A Pier | 2020-11-02 | 2021-06-16 | 226
TFD-004 ¦ CTA Expansion - A Pier | 2021-04-12 | 2021-12-17 |  | 249
TFD-005 ¦ Terminal C Renovation Phase 1 | 2022-01-10 | 2023-01-10 | 366
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2020-11-02 | 2023-01-11 | 800
TFD-006 ¦ CTA Exp-Term C Reno 2-26 | 2021-08-06 | 2023-05-28 |  | 660
TFD-007 ¦ CTA Exp-Term C Garage South | 2020-11-02 | 2021-06-16 | 226
TFD-007 ¦ CTA Exp-Term C Garage South | 2021-07-19 | 2021-08-25 |  | 38
TFD-008 ¦ CTA Exp-Utility Corr | 2020-11-02 | 2021-05-25 | 204
TFD-008 ¦ CTA Exp-Utility Corr | 2021-05-26 | 2021-08-25 |  | 90
TFD-008 ¦ CTA Exp-Utility Corr | 2021-08-26 | 2022-12-02 |  |  | 464
TFD-009 ¦ CTA Exp-Term E Gate Swap | 2020-07-13 | 2021-06-14 | 336
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2020-11-02 | 2021-01-14 | 74
TFD-010 ¦ AA Terminal BHS & Staff Fitout | 2021-03-01 | 2021-12-17 |  | 291
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2020-11-02 | 2021-01-14 | 74
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2021-03-01 | 2021-12-17 |  | 292
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2021-12-17 | 2022-10-03 |  |  | 291
TFD-011 ¦ CTA Expansion - Program Integration Office (PIO) | 2022-10-03 | 2022-10-27 |  |  |  | 24
TFF-001 ¦ Terminal F West Concourse & Skylink Station | 2021-11-09 | 2023-05-18 | 556
TFF-002 ¦ Terminal E Reconfiguration | 2021-11-09 | 2023-05-18 | 556
TFF-003 ¦ Terminal F Civil & Utility | 2021-11-09 | 2023-05-18 | 556
TFF-004 ¦ BHS, Goods Delivery & Services* | 2021-11-09 | 2023-05-18 | 556
TFF-005 ¦ Terminal D Bus Station | 2021-11-09 | 2023-05-18 | 556
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2021-11-09 | 2023-05-18 | 556
TFF-006 ¦ DFW Southwest Hardstands Relocation | 2022-12-01 | 2023-01-08 |  | 39
TRIP-09 ¦ TRIP - Terminal A Pet Conveyor | 2017-09-01 | 2017-11-02 |  | 63
TRIP-12 ¦ TRIP - Parking Lot Removal | 2018-07-16 | 2019-01-04 |  |  | 173
TRIP-12 ¦ TRIP - Parking Lot Removal | 2019-01-06 | 2019-07-15 |  |  |  | 190
TRIP-12 ¦ TRIP - Parking Lot Removal | 2019-07-22 | 2021-10-15 |  |  |  |  | 816
UTL-004-B ¦ Landside Storm Sewer Repair | 2020-12-02 | 2020-12-22 | 21
UTL-004-B ¦ Landside Storm Sewer Repair | 2020-12-12 | 2021-02-10 |  | 61
UTL-004-B ¦ Landside Storm Sewer Repair | 2021-02-11 | 2022-08-06 |  |  | 541
UTL-004-B ¦ Landside Storm Sewer Repair | 2022-08-07 | 2023-03-21 |  |  |  | 227
UTL-017 ¦ Rehabilitate Open Channels | 2019-11-03 | 2022-06-01 | 941
UTL-017 ¦ Rehabilitate Open Channels | 2022-06-01 | 2022-06-02 |  | 1
UTL-017 ¦ Rehabilitate Open Channels | 2022-06-03 | 2022-06-04 |  |  | 1
UTL-017 ¦ Rehabilitate Open Channels | 2022-06-05 | 2022-06-06 |  |  |  | 1
UTL-017 ¦ Rehabilitate Open Channels | 2022-06-06 | 2023-03-03 |  |  |  |  | 271
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2018-12-20 | 2019-03-12 |  | 82
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2019-03-12 | 2019-08-02 |  |  | 143
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2019-08-17 | 2020-01-10 |  |  |  | 146
UTL-024-Ab ¦ High Mast Lighting Pole Rehabilitation/Replacement (Phase I) | 2020-01-13 | 2023-05-31 |  |  |  |  | 1235
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2021-05-07 | 2021-05-31 | 24
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2021-06-01 | 2021-06-28 |  | 27
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2021-06-28 | 2022-02-20 |  |  | 237
UTL-037 ¦ Energy Plaza Water Condenser | 2017-11-14 | 2019-06-13 |  | 577
UTL-037 ¦ Energy Plaza Water Condenser | 2019-06-14 | 2020-03-06 |  |  | 266
UTL-037 ¦ Energy Plaza Water Condenser | 2021-01-10 | 2021-08-13 |  |  |  | 216
UTL-037 ¦ Energy Plaza Water Condenser | 2021-08-25 | 2023-03-26 |  |  |  |  | 578
UTL-045 ¦ East & West Potable Water Pump Stations | 2017-05-24 | 2021-02-27 |  |  | 1375
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2022-02-08 | 2022-06-25 | 137
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2022-06-26 | 2022-09-29 |  | 96
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2021-04-28 | 2021-06-09 | 42
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2021-06-18 | 2021-12-08 |  | 173
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2021-12-06 | 2022-05-16 |  |  | 162
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2022-05-22 | 2022-10-18 |  |  |  | 149
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2022-07-11 | 2022-10-09 | 91
UTL-169 ¦ Rehabilitate Existing MS10.0B Inverted Siphon | 2022-10-17 | 2023-01-12 |  | 88
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2019-09-12 | 2020-04-28 | 230
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2020-06-08 | 2020-11-08 |  | 154
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2020-12-10 | 2022-07-11 |  |  | 579
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2022-07-05 | 2023-02-20 |  |  |  | 231
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2023-02-20 | 2023-06-02 |  |  |  |  | 102
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2020-01-10 | 2020-09-04 | 238
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2020-09-08 | 2020-12-16 |  | 99
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2020-12-17 | 2021-07-17 |  |  | 213
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2021-07-18 | 2022-05-06 |  |  |  | 293
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2022-06-01 | 2023-02-28 |  |  |  |  | 273
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2022-05-06 | 2023-02-01 | 272
UTL-207 ¦ Data Center and Terminal D UPS Replacement | 2023-02-09 | 2023-04-12 |  | 63
AFD-045 ¦ Spent Aircraft Deicing Fluid (SADF) Storage and Treatment | 2022-05-22 | 2023-06-19 | 394
AFD-048-A ¦ Southwest End-Around Taxiway Project | 2023-01-03 | 2024-01-11 |  |  |  |  | 374
AFD-050-B ¦ NE End-Around Taxiway Package II - Taxiway Papa Realignment | 2022-03-31 | 2023-07-22 | [5 empty] | 479
AFD-050-C ¦ NE End-Around Taxiway Package III - Glycol Facilities Relocation | 2020-10-01 | 2023-08-01 | [5 empty] | 1035
AFD-062-A ¦ RWY 17C/35C Reconstruction -Taxiway Mike North (Const. Pkg. - III) | 2016-11-07 | 2023-11-29 |  |  | 2578
AFD-062-B ¦ RWY 17C/35C Reconstruction -Taxiway Mike South (Const. Pkg. - II) | 2021-05-15 | 2023-07-31 | [5 empty] | 808
AFD-102 ¦ Taxiway F Rehabilitation | 2022-03-01 | 2023-09-30 | [5 empty] | 579
AFD-124 ¦ Taxiway G Emergency Repair | 2021-06-11 | 2023-09-30 | [5 empty] | 842
AFD-138 ¦ Collapsed Soil Sites Rehabilitation II | 2022-05-31 | 2023-06-24 |  |  |  |  | 390
AFD-141 ¦ Airfield Pavement Remediation | 2022-07-14 | 2023-06-24 |  |  |  |  | 346
NCOM-040 ¦ 19th Street Cargo Redevelopment | 2022-02-14 | 2023-08-08 |  |  | 541
NOTH-067 ¦ RCC Restroom Renovations | 2022-09-16 | 2023-06-30 | [5 empty] | 288
NOTH-075 ¦ Rental Car Center - Restroom Renovations Phase II | 2022-11-07 | 2023-12-10 |  |  |  |  | 399
NOTH-089 ¦ Cellular DAS Headend Move to 5E | 2023-03-09 | 2023-07-14 |  | 128
NTER-224 ¦ Terminal D - CBP Arrivals Hall Carpet Replacement | 2023-02-13 | 2023-08-02 | 171
NTER-299-A ¦ Sewer, Condensate and Ventilation Issues Remediation in B & E | 2022-08-06 | 2023-06-26 | [5 empty] | 325
NTER-300 ¦ One-Stop Security (OSS) Pax Navigation Options Implementation | 2023-06-05 | 2023-09-28 |  |  | 116
NTER-302 ¦ Terminal Exit Lane Installation | 2023-05-02 | 2023-08-29 | [5 empty] | 120
OTH-026-C ¦ DFW Facilities Relocation and Consolidation - Phase 1 Roads and Utilities | 2021-10-18 | 2023-09-29 | [5 empty] | 712
OTH-072 ¦ Bird Deterrent Systems Along the Skylink Guideway | 2023-03-12 | 2023-07-22 |  |  |  | 133
OTH-073 ¦ Reconfigure Storm Water System at various locations. | 2022-07-12 | 2023-09-15 |  |  |  |  | 431
OTH-078 ¦ Skylink UPSs Replacement | 2022-11-15 | 2023-07-01 | [5 empty] | 229
OTH-083 ¦ Indoor Air Quality HVAC Improvements at Non-Terminal Facilities | 2022-10-29 | 2023-08-11 | [5 empty] | 287
OTH-086 ¦ Old Conveyances Replacement | 2022-10-14 | 2023-07-10 |  | 270
PAR-069 ¦ Overhead Vertical Height Clearance Sign Enhancements | 2023-05-17 | 2023-09-13 | [5 empty] | 120
PSR-002 ¦ Northwest Cargo Redevelopment - Phase 1 | 2022-01-31 | 2023-08-01 | [5 empty] | 548
RDS-001 ¦ Skylink ATC Replacement | 2020-09-30 | 2023-11-07 |  |  |  |  | 1133
RDS-007 ¦ East West Connector Roadway | 2023-02-05 | 2023-07-07 |  |  |  | 153
RDS-008 ¦ Repair of Southbound Ramp to Crossover #4 Retaining Wall | 2022-10-28 | 2023-09-09 | [5 empty] | 317
RDS-015 ¦ Rehabilitate Landside Roadways & Bridges Phase 4A | 2022-10-28 | 2023-07-11 | [5 empty] | 257
RDS-016 ¦ Landside Roads & Bridges Rehabilitation Phase 4b | 2022-10-28 | 2023-07-11 | [5 empty] | 257
RDS-025 ¦ Cloverleafs & Ramps North Airfield Drive Bridge | 2022-02-27 | 2023-08-10 |  |  |  | 530
RDS-029-A ¦ Glade Road Reconstruction Utilities Relocation | 2021-06-03 | 2023-08-29 | [5 empty] | 818
RDS-029-B ¦ Glade Road and Bridge Replacement | 2022-02-28 | 2023-06-23 |  |  |  |  | 481
RDS-045 ¦ Terminal D Upper Level Roadway & Sidewalks Expansion Joint Replacement | 2021-07-18 | 2023-09-30 | [5 empty] | 805
RDS-050-A ¦ Skylink Structural Improvements | 2018-06-19 | 2024-09-13 |  |  |  |  | 2279
RDS-067-A ¦ Replacement of 2 Flyover Bridges to Terminals A & E | 2022-02-04 | 2023-08-04 |  |  |  |  | 547
RDS-067-A ¦ Replacement of 2 Flyover Bridges to Terminals A & E | 2023-02-04 | 2024-05-20 |  |  |  |  | 472
RDS-067 ¦ International Parkway Flyover Bridges Replacement | 2022-10-29 | 2023-08-11 |  |  |  | 287
RDS-186-B ¦ Soil Slopes Remediation Phase 2 | 2022-04-15 | 2023-09-17 |  |  |  |  | 521
RDS-188 ¦ Rehabilitation of DFW Bridge 6-3E | 2023-02-10 | 2023-07-28 | [5 empty] | 169
SAF-012 ¦ DPS Police Outdoor Range Upgrade | 2023-03-06 | 2023-12-31 |  |  |  |  | 301
SAF-028 ¦ Integrated AOC-EOC Center | 2021-01-07 | 2023-09-27 | [5 empty] | 994
SAF-051 ¦ Fire Training Research Center Rehabilitation | 2022-10-28 | 2023-09-01 |  |  | 309
SAF-066 ¦ Curbside Barrier Installation | 2022-09-01 | 2023-07-31 | [5 empty] | 334
SAF-078 ¦ Employee Inspection Portal Redesign | 2022-09-29 | 2024-01-22 |  |  |  |  | 481
TER-007 ¦ Terminal B & E Replace Passenger Boarding Bridges (PBBs) B9B, B10B, E31, & E34 | 2021-09-16 | 2023-07-31 | [5 empty] | 684
TER-021-A ¦ Term-D Systems Rehabilitation | 2022-06-21 | 2023-06-30 | [5 empty] | 375
TER-067 ¦ Term-A Roofing Project | 2021-11-04 | 2024-10-20 |  |  |  |  | 1082
TER-072 ¦ Upgrade Passenger Boarding Bridge (PBBs) Equipment - Terminal E | 2021-11-25 | 2023-09-29 | [5 empty] | 674
TER-155 ¦ Electrical Power Upgrade - Terminal D | 2019-10-10 | 2023-06-19 | [5 empty] | 1349
TER-160 ¦ Terminal D Board Owned PBB Rehab | 2020-07-03 | 2023-08-31 | [5 empty] | 1155
TER-176 ¦ Terminal D UPS Replacement | 2020-10-19 | 2023-06-19 | [5 empty] | 974
TER-208 ¦ Skylink Stations A, B, C and E HVAC Control System Replacement | 2023-05-15 | 2023-08-04 |  | 82
TER-261 ¦ Terminal A, B, C, and E Waterproofing Project | 2021-02-09 | 2023-06-30 |  |  |  |  | 872
TER-262 ¦ DFW Rental Car Service Site Hail Canopy | 2022-09-05 | 2023-08-11 | [5 empty] | 341
TER-273 ¦ Sky-link Restrooms Initiative | 2020-06-03 | 2023-12-13 |  |  |  |  | 1289
TER-274-A ¦ Passenger Boarding Bridge Program #1 - Phase 2 | 2022-12-05 | 2023-10-14 |  |  | 314
TER-281 ¦ 2020 Term-D End of Life Elect & Mech Systems | 2022-08-25 | 2023-07-15 | [5 empty] | 325
TER-283 ¦ Terminal D Plumbing and Mechanical Equipment Replacement | 2023-04-24 | 2023-09-23 |  |  |  | 153
TER-284 ¦ Terminal A, B, C, D, E UPS Replacements | 2023-02-26 | 2023-08-29 | [5 empty] | 185
TER-286 ¦ Terminal Electrical Systems Upgrade | 2023-01-23 | 2023-08-25 | [5 empty] | 215
TER-289 ¦ Terminal D and Garage Dry Sprinkler System | 2022-02-02 | 2023-09-13 |  |  | 589
TER-297 ¦ Term-D Sewer Lift Station | 2022-04-19 | 2023-08-18 |  |  |  |  | 487
TER-301 ¦ Skylink Elevator Replacement Project | 2022-11-14 | 2023-11-08 |  |  | 360
TF2-003 ¦ Programatic EA-NEPA | 2020-03-02 | 2023-07-07 |  |  | 1223
TRIP-12 ¦ TRIP - Parking Lot Removal | 2021-10-18 | 2023-09-29 | [5 empty] | 712
UTL-004-B ¦ Landside Storm Sewer Repair | 2023-03-28 | 2023-07-10 |  |  |  |  | 105
UTL-024-B ¦ High Pole Lighting Replacement (Phase II) | 2022-02-20 | 2023-08-11 |  |  |  | 538
UTL-037 ¦ Energy Plaza Water Condenser | 2023-03-27 | 2023-08-29 | [5 empty] | 156
UTL-128 ¦ Rehabilitate Energy Plaza Control Automation System | 2022-08-01 | 2023-06-30 |  |  | 334
UTL-146 ¦ Terminal D Parking Garage Lighting Upgrade | 2022-10-19 | 2023-07-19 |  |  |  |  | 274
UTL-199 ¦ Install 8-inch Sewer main from North Remote Parking to North Control Plaza | 2023-06-03 | 2023-10-01 | [5 empty] | 121
UTL-200 ¦ Reconstruction of the North Sludge Pond | 2023-03-01 | 2023-06-22 | [5 empty] | 114
AFD-142 ¦ Taxiway G Rehabilitation | 2022-03-23 | 2023-12-27 | 645
PSR-057 ¦ West 21st Street Repairs | 2022-10-05 | 2023-11-30 |  |  |  |  | 422
TER-185 ¦ Terminal E-Satellite (excludes metal roof) | 2018-05-01 | 2024-01-02 |  |  |  |  | 2073
TER-255 ¦ Terminal B Mainline Expansion | 2018-12-19 | 2024-01-02 |  |  |  |  | 1841
TER-258-A ¦ Program Development for Baggage Handling System Improvements | 2020-12-01 | 2024-09-30 |  |  |  |  | 1400